## Overview
Task/Activity | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Requirement Analysis & Solution Design | bar: 2022-10-01
Application Development | bar: 2022-11-01 to 2023-02-01
SIT | bar: 2023-01-01 to 2023-02-01
UAT 1 | bar: 2023-02-01
UAT 2 | bar: 2023-03-01
Deployment | bar: 2023-03-01

## API List
S No | Page | Method | API | API Status | Angular Status | Remark
1 | Alert | GET | /webSite/getAll?operation=alert | Completed | Completed
2 | Alert | POST | /webSite/alerts?operation=add | Completed | Completed
3 | Master | GET | /getAll?operation=users | Completed | Completed
4 | Master | GET | /getAll?operation=menus | Completed | Completed
5 | Master | GET | /getAll?operation=subMenus | Completed | Completed
6 | Master | GET | /getAll?operation=roles | Completed | Completed
7 | Master | GET | /getAll?operation=pemissions | Completed | Completed
8 | Master | POST | /user?operation=add | Completed | Completed
9 | Master | POST | /user?operation=save | Completed | Completed
10 | Master | POST | /user?operation=active | Completed | Completed
11 | Master | POST | /user?operation=delete | Completed | Completed
12 | Master | POST | /menus?operation=add | Completed | Completed
13 | Master | POST | /menus?operation=save | Completed | Completed
14 | Master | POST | /menus?operation=active | Completed | Completed
15 | Master | POST | /menus?operation=delete | Completed | Completed
16 | Master | POST | /role?operation=add | Completed | Completed
17 | Master | POST | /role?operation=save | Completed | Completed
18 | Master | POST | /role?operation=active | Completed | Completed
19 | Master | POST | /role?operation=delete | Completed | Completed
20 | Master | POST | /subMenu?operation=add | Completed | Completed
21 | Master | POST | /subMenu?operation=save | Completed | Completed
22 | Master | POST | /subMenu?operation=active | Completed | Completed
23 | Master | POST | /subMenu?operation=delete | Completed | Completed
24 | Master | POST | /rolePermissions?roleId= | Completed | Completed
25 | Master | POST | /saveRolePermission | Completed | Completed
26 | Master | POST | /saveDefaultRolePermission | Completed | Completed
27 | Student | GET | /student/getAll?operation=student | Completed | Completed
28 | Student | GET | /student/getAll?operation=course | Completed | Completed
29 | Student | GET | /student/getAll?operation=donation | Completed | Completed
30 | Student | GET | /student/getAll?operation=ePurchase | Completed | Completed
31 | Student | POST | /student/profile | Completed | Completed
32 | Student | POST | /student/donation | Completed | Completed
33 | Student | POST | /student/purchase | Completed | Completed
34 | Student | POST | /student/volunteer | Completed | Completed
35 | Login | POST | /login | Completed | Completed
36 | Login | GET | /logout | Completed | Completed
37 | Login | POST | /changePassword | Completed | Completed
38 | Black List | GET | /student/getAll?operation=blackListUser | Completed | Completed
39 | Black List | POST | /student/blockListUsers?operation=add | Completed | Completed
40 | Black List | POST | /student/blockListUsers?operation=delete | Completed | Completed
41 | Banner | GET | /webSite/getAll?operation=banner | Completed | Completed
42 | Banner | POST | /webSite/banner?operation=add | In progress | In progress | Primary Key Missing
43 | Donation | GET | /student/getAll?operation=donation | Completed | In progress | updated
44 | Donation | POST | /student/donationView | Completed | In progress | updated
45 | Course | GET | /course/getAll?operation=courseCategory | Completed | In progress | New
46 | Course | POST | /course/addCourse | Completed | In progress | New
47 | Class Media | GET | /course/getAll?operation=classMedia | Completed | In progress | New
48 | Course Media | GET | /course/getAll?operation=courseMediaCategory | Completed | In progress | New
49 | Course Media | POST | /course/addCourseMedia?type=video | Completed | In progress | New
50 | Course Media | POST | /course/addCourseMedia?type=shortVideo | Completed | In progress | New
51 | Course Media | POST | /course/addCourseMedia?type=glimpses | Completed | In progress | New
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Detailed Plan
S.No | Module | Task Details | Member | Frontend/API | Status | Start Date | End Date | Resource | Remarks
2 | Admin | Role | Sumukesh | API | Completed | 2022-10-31 | 2022-10-31 | JAVA-1
4 | Admin | Registration | Sumukesh | API | Completed | 2022-10-31 | 2022-10-31 | JAVA-2
6 | Admin | Role Permission | Sumukesh | API | Completed | 2022-11-01 | 2022-11-01 | JAVA-1
8 | Admin | Menu | Sumukesh | API | Completed | 2022-11-01 | 2022-11-01 | JAVA-2
3 | Admin | Role | Shekar | Frontend | Completed | 2022-11-02 | 2022-11-02 | ANGULAR-1
5 | Admin | Registration | Shekar | Frontend | Completed | 2022-11-02 | 2022-11-02 | ANGULAR-2
10 | Admin | Sub-Menu | Sumukesh | API | Completed | 2022-11-02 | 2022-11-02 | JAVA-1
12 | Admin | User | Sumukesh | API | Completed | 2022-11-02 | 2022-11-02 | JAVA-2
7 | Admin | Rolepermission | Shekar | Frontend | Completed | 2022-11-03 | 2022-11-03 | ANGULAR-1
9 | Admin | Menu | Shekar | Frontend | Completed | 2022-11-03 | 2022-11-03 | ANGULAR-2
14 | Admin | DashBoard - Course Resport | Sumukesh | API | Completed | 2022-11-16 | 2022-11-03 | JAVA-1
16 | Admin | DashBoard - OverallReport | Sumukesh | API | Completed | 2022-11-16 | 2022-11-03 | JAVA-2
11 | Admin | Sub-menu | Shekar | Frontend | Completed | 2022-11-04 | 2022-11-04 | ANGULAR-1
13 | Admin | User | Shekar | Frontend | Completed | 2022-11-04 | 2022-11-04 | ANGULAR-2
15 | Admin | DashBoard - Course Resport | Shekar | Frontend | Completed | 2022-11-07 | 2022-11-07 | ANGULAR-1
17 | Admin | DashBoard - OverallReport | Shekar | Frontend | Completed | 2022-11-07 | 2022-11-07 | ANGULAR-2
22 | Admin | View student | Sumukesh | API | Completed | 2022-11-16 | 2022-11-07 | JAVA-1
24 | Admin | View Student - Course Profile | Sumukesh | API | Completed | 2022-11-16 | 2022-11-07 | JAVA-2
26 | Admin | View Student -Donation | Praneeth | API | Completed | 2022-11-16 | 2022-11-08 | JAVA-1
28 | Admin | View Student- e-purchases Information | Praneeth | API | Completed | 2022-11-16 | 2022-11-08 | JAVA-2
23 | Admin | View student | Shekar | Frontend | Completed | 2022-11-09 | 2022-11-09 | ANGULAR-1
30 | Admin | View Student - Add Purchases | Sumukesh | API | Completed | 2022-11-16 | 2022-11-09 | JAVA-1
32 | Admin | View Student- Volunteering details | Sumukesh | API | Completed | 2022-11-16 | 2022-11-09 | JAVA-2
1 | Common | Analysis & Design (DB, Application, UI) |  |  | In Progress | 2022-10-13 | 2022-11-10
27 | Admin | View Student -Donation | Shekar | Frontend | Completed | 2022-11-10 | 2022-11-10 | ANGULAR-1
29 | Admin | View Student- e-purchases Information | Shekar | Frontend | Completed | 2022-11-10 | 2022-11-10 | ANGULAR-2
34 | Admin | View Student -Add Volunteer | Praneeth | API | Completed | 2022-11-16 | 2022-11-10 | JAVA-1
36 | Admin | View student - Permonce report | Sumukesh | API | In Progress | 2022-11-16 | 2022-11-10 | JAVA-2
37 | Admin | Alerts | Ajith R | Frontend | Completed | 2022-11-14 | 2022-11-14 | ANGULAR-2 | Completed But yet to be commited
25 | Admin | View Student - Course Profile | Shekar | Frontend | Completed | 2022-11-09 | 2022-11-16 | ANGULAR-2
31 | Admin | View Student - Add Purchases | Shekar | Frontend | Completed | 2022-11-11 | 2022-11-16 | ANGULAR-1
33 | Admin | View Student- Volunteering details | Shekar | Frontend | Completed | 2022-11-11 | 2022-11-16 | ANGULAR-2
35 | Admin | View student - Permonce report | Shekar | Frontend | Completed | 2022-11-14 | 2022-11-16 | ANGULAR-1
39 | Admin | Audio Management - Audio Dharanas | Ajith R | Frontend | Completed | 2022-11-15 | 2022-11-16 | ANGULAR-1 | Completed But yet to be commited
41 | Admin | Banners | Ajith R | Frontend | Completed | 2022-11-15 | 2022-11-16 | ANGULAR-2 | Completed But yet to be commited
43 | Admin | Add Banner | Ajith Kumar | Frontend | Completed | 2022-11-16 | 2022-11-16 | ANGULAR-1
38 | Admin | Alerts | Praneeth/Karthik | API | Completed | 2022-11-11 | 2022-11-17 | JAVA-1
40 | Admin | Audio Management - Audio Dharanas | Sumukesh | API | In Progress | 2022-11-11 | 2022-11-17 | JAVA-2 | Only Upload
42 | Admin | Banners | Praneeth/karthik | API | Completed | 2022-11-14 | 2022-11-17 | JAVA-1
44 | Admin | Add Banner | Sumukesh/karthik | API | In Progress | 2022-11-14 | 2022-11-17 | JAVA-2 | Clarification Needed
45 | Admin | Black List users | Ajith Kumar | Frontend | Completed | 2022-11-16 | 2022-11-17 | ANGULAR-2
47 | Admin | Class Media Update | Ajith R | Frontend | Completed | 2022-11-17 | 2022-11-17 | ANGULAR-1 | Completed But yet to be commited
49 | Admin | Course Media Live Class | Ajith R | Frontend | Completed | 2022-11-17 | 2022-11-17 | ANGULAR-2 | Completed But yet to be commited
46 | Admin | Black List users | Praneeth/Ajith K | API | Completed | 2022-11-15 | 2022-11-18 | JAVA-1
48 | Admin | Class Media Update | Sumukesh/Ajith K | API | Completed | 2022-11-15 | 2022-11-18 | JAVA-2 | Pending Angular Binding
50 | Admin | Course Media Live Class | Praneeth/ karthik | API | Completed | 2022-11-16 | 2022-11-18 | JAVA-1 | Pending Angular Binding
51 | Admin | Course Media Practice sessions | Ajith Kumar | Frontend | Completed | 2022-11-18 | 2022-11-18 | ANGULAR-1
52 | Admin | Course Media Practice sessions | Sumukesh/Ajith K | API | In Progress | 2022-11-16 | 2022-11-18 | JAVA-2
53 | Admin | Courses | Ajith Kumar | Frontend | Completed | 2022-11-18 | 2022-11-18 | ANGULAR-2
54 | Admin | Courses | Praneeth/Ajith R | API | Completed | 2022-11-17 | 2022-11-21 | JAVA-1 | Pending Angular Binding
55 | Admin | Add Course / View Course details | Ajith R | Frontend | Completed | 2022-11-21 | 2022-11-21 | ANGULAR-1
56 | Admin | Add Course / View Course details | Sumukesh/Ajith R | API | Completed | 2022-11-17 | 2022-11-21 | JAVA-2 | Pending Angular Binding
57 | Admin | Create a Practice Library | Karthik | Frontend | Completed | 2022-11-21 | 2022-11-21 | ANGULAR-2
58 | Admin | Create a Practice Library | Praneeth | API | Pending | 2022-11-18 | 2022-11-21 | JAVA-1
60 | Admin | List of Practice library | Sumukesh | API | Pending | 2022-11-18 | 2022-11-21 | JAVA-2
62 | Admin | Create scripctures | Praneeth | API | In Progress | 2022-11-21 | 2022-11-21 | JAVA-1 | Clarification Needed
64 | Admin | Donations management | Sumukesh/ Ajith K | API | Completed | 2022-11-21 | 2022-11-21 | JAVA-2 | Pending Angular Binding
66 | Admin | View details | Sumukesh / Karthik | API | Completed | 2022-11-21 | 2022-11-21 | JAVA-1 | Pending Angular Binding
59 | Admin | List of Practice library | Ajith Kumar | Frontend | Completed | 2022-11-22 | 2022-11-22 | ANGULAR-1
61 | Admin | Create scripctures | Karthik | Frontend | Completed | 2022-11-22 | 2022-11-22 | ANGULAR-2
68 | Admin | Hide Menu Option |  | API | Pending | 2022-11-22 | 2022-11-22 | JAVA-2
70 | Admin | Map user to course |  | API | Pending | 2022-11-22 | 2022-11-22 | JAVA-1
63 | Admin | Donations management | Ajith Kumar | Frontend | In Progress | 2022-11-23 | 2022-11-23 | ANGULAR-1
65 | Admin | View details | Karthik | Frontend | In Progress | 2022-11-23 | 2022-11-23 | ANGULAR-2
72 | Admin | Members |  | API | Pending | 2022-11-23 | 2022-11-23 | JAVA-2
74 | Admin | Mentor mapping |  | API | Pending | 2022-11-23 | 2022-11-23 | JAVA-1
67 | Admin | Hide Menu Option | Karthik | Frontend | In Progress | 2022-11-24 | 2022-11-24 | ANGULAR-1
69 | Admin | Map user to course | Ajith R | Frontend | In Progress | 2022-11-24 | 2022-11-24 | ANGULAR-2
76 | Admin | My Course Metrials |  | API | Pending | 2022-11-24 | 2022-11-24 | JAVA-2
78 | Admin | Notifications |  | API | Pending | 2022-11-24 | 2022-11-24 | JAVA-1
71 | Admin | Members | karthik | Frontend | Pending | 2022-11-25 | 2022-11-25 | ANGULAR-1
73 | Admin | Mentor mapping | Ajith R | Frontend | Pending | 2022-11-25 | 2022-11-25 | ANGULAR-2
75 | Admin | My Course Metrials | Ajith Kumar | Frontend | Pending | 2022-11-28 | 2022-11-28 | ANGULAR-1
77 | Admin | Notifications | karthik | Frontend | Pending | 2022-11-28 | 2022-11-28 | ANGULAR-2
80 | Admin | Online Exams |  | API | Pending | 2022-11-28 | 2022-11-28 | JAVA-2
82 | Admin | Pages1 |  | API | Pending | 2022-11-28 | 2022-11-28 | JAVA-1
79 | Admin | Online Exams |  | Frontend | Pending | 2022-11-29 | 2022-11-29 | ANGULAR-1
81 | Admin | Pages1 |  | Frontend | Pending | 2022-11-29 | 2022-11-29 | ANGULAR-2
84 | Admin | Pages2 |  | API | Pending | 2022-11-29 | 2022-11-29 | JAVA-2
86 | Admin | Parameters |  | API | Pending | 2022-11-29 | 2022-11-29 | JAVA-1
83 | Admin | Pages2 |  | Frontend | Pending | 2022-11-30 | 2022-11-30 | ANGULAR-1
85 | Admin | Parameters |  | Frontend | Pending | 2022-11-30 | 2022-11-30 | ANGULAR-2
88 | Admin | pearls of wisdom |  | API | Pending | 2022-11-30 | 2022-11-30 | JAVA-2
90 | Admin | Photo gallery |  | API | Pending | 2022-11-30 | 2022-11-30 | JAVA-1
87 | Admin | pearls of wisdom |  | Frontend | Pending | 2022-12-01 | 2022-12-01 | ANGULAR-1
89 | Admin | Photo gallery |  | Frontend | Pending | 2022-12-01 | 2022-12-01 | ANGULAR-2
92 | Admin | Upload image to gallery |  | API | Pending | 2022-12-01 | 2022-12-01 | JAVA-2
94 | Admin | Create gallery |  | API | Pending | 2022-12-01 | 2022-12-01 | JAVA-1
91 | Admin | Upload image to gallery |  | Frontend | Pending | 2022-12-02 | 2022-12-02 | ANGULAR-1
93 | Admin | Create gallery |  | Frontend | Pending | 2022-12-02 | 2022-12-02 | ANGULAR-2
96 | Admin | Regions Creation |  | API | Pending | 2022-12-02 | 2022-12-02 | JAVA-2
98 | Admin | Mapping regions to Chief mentor |  | API | Pending | 2022-12-02 | 2022-12-02 | JAVA-1
95 | Admin | Regions Creation |  | Frontend | Pending | 2022-12-05 | 2022-12-05 | ANGULAR-1
97 | Admin | Mapping regions to Chief mentor |  | Frontend | Pending | 2022-12-05 | 2022-12-05 | ANGULAR-2
100 | Admin | Chief metor mapping |  | API | Pending | 2022-12-05 | 2022-12-05 | JAVA-2
102 | Admin | Task Assignment |  | API | Pending | 2022-12-05 | 2022-12-05 | JAVA-1
99 | Admin | Chief metor mapping |  | Frontend | Pending | 2022-12-06 | 2022-12-06 | ANGULAR-1
101 | Admin | Task Assignment |  | Frontend | Pending | 2022-12-06 | 2022-12-06 | ANGULAR-2
104 | Admin | Create Task |  | API | Pending | 2022-12-06 | 2022-12-06 | JAVA-2
106 | Admin | Testimonials |  | API | Pending | 2022-12-06 | 2022-12-06 | JAVA-1
103 | Admin | Create Task |  | Frontend | Pending | 2022-12-07 | 2022-12-07 | ANGULAR-1
105 | Admin | Testimonials |  | Frontend | Pending | 2022-12-07 | 2022-12-07 | ANGULAR-2
108 | Admin | Add Testimonial |  | API | Pending | 2022-12-07 | 2022-12-07 | JAVA-2
110 | Admin | Users - Search Filter |  | API | Pending | 2022-12-07 | 2022-12-07 | JAVA-1
107 | Admin | Add Testimonial |  | Frontend | Pending | 2022-12-08 | 2022-12-08 | ANGULAR-1
109 | Admin | Users - Search Filter |  | Frontend | Pending | 2022-12-08 | 2022-12-08 | ANGULAR-2
112 | Admin | Users - Find suspicious users |  | API | Pending | 2022-12-08 | 2022-12-08 | JAVA-2
114 | Admin | create album for videos |  | API | Pending | 2022-12-08 | 2022-12-08 | JAVA-1
111 | Admin | Users - Find suspicious users |  | Frontend | Pending | 2022-12-09 | 2022-12-09 | ANGULAR-1
116 | Admin | Add videos for gallery page |  | API | Pending | 2022-12-09 | 2022-12-09 | JAVA-2
118 | Admin | Video gallery1 |  | API | Pending | 2022-12-09 | 2022-12-09 | JAVA-1
113 | Admin | create album for videos |  | Frontend | Pending | 2022-12-12 | 2022-12-12 | ANGULAR-2
115 | Admin | Add videos for gallery page |  | Frontend | Pending | 2022-12-12 | 2022-12-12 | ANGULAR-1
120 | Admin | Video gallery2 |  | API | Pending | 2022-12-12 | 2022-12-12 | JAVA-2
122 | Admin | Hide Options (hide some menu options like retreat and courses) for few some students or multiple students |  | API | Pending | 2022-12-12 | 2022-12-12 | JAVA-1
117 | Admin | Video gallery1 |  | Frontend | Pending | 2022-12-13 | 2022-12-13 | ANGULAR-2
119 | Admin | Video gallery2 |  | Frontend | Pending | 2022-12-13 | 2022-12-13 | ANGULAR-1
124 | Admin | Access controls - worldwide aplications not visible for few chief Mentors |  | API | Pending | 2022-12-13 | 2022-12-13 | JAVA-2
121 | Admin | Hide Options (hide some menu options like retreat and courses) for few some students or multiple students |  | Frontend | Pending | 2022-12-14 | 2022-12-14 | ANGULAR-2
123 | Admin | Access controls - worldwide aplications not visible for few chief Mentors |  | Frontend | Pending | 2022-12-14 | 2022-12-14 | ANGULAR-1
125 | Admin | Bulk upload option whereever applicable |  | Frontend | Pending | 2022-12-16 | 2022-12-16 | ANGULAR-2
127 | Admin | Automatic allocation of mentor - defining gratitude day for mentor and chief mentor (mapping) |  | Frontend | Pending | 2022-12-16 | 2022-12-16 | ANGULAR-1
126 | Admin | Bulk upload option whereever applicable |  | API | Pending | 2022-12-19 | 2022-12-19 | JAVA-1
128 | Admin | Automatic allocation of mentor - defining gratitude day for mentor and chief mentor (mapping) |  | API | Pending | 2022-12-19 | 2022-12-19 | JAVA-2
129 | Admin | Maximum view of lists n every page |  | Frontend | Pending | 2022-12-19 | 2022-12-19 | ANGULAR-2
131 | Admin | Website Managemennt: gallary management and video management |  | Frontend | Pending | 2022-12-19 | 2022-12-19 | ANGULAR-1
130 | Admin | Maximum view of lists n every page |  | API | Pending | 2022-12-20 | 2022-12-20 | JAVA-1
132 | Admin | Website Managemennt: gallary management and video management |  | API | Pending | 2022-12-20 | 2022-12-20 | JAVA-2
133 | Admin | Free enrollment or Paid Enrollment option for student to particular course |  | Frontend | Pending | 2022-12-20 | 2022-12-20 | ANGULAR-2
135 | Admin | Exceptional registrations in the mid of the course by Admin |  | Frontend | Pending | 2022-12-20 | 2022-12-20 | ANGULAR-1
134 | Admin | Free enrollment or Paid Enrollment option for student to particular course |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-1
136 | Admin | Exceptional registrations in the mid of the course by Admin |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-2
20 | Admin | Manage Exemptions |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-2
21 | Admin | Manage Exemptions |  | Frontend | Pending | 2022-12-21 | 2022-12-21 | ANGULAR-2
137 | Student | Dashboard |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-1
139 | Student | Class |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-2
138 | Student | Dashboard |  | Frontend | Pending | 2022-12-22 | 2022-12-22 | ANGULAR-1
140 | Student | Class |  | Frontend | Pending | 2022-12-22 | 2022-12-22 | ANGULAR-2
141 | Student | Cources Details |  | API | Pending | 2022-12-22 | 2022-12-22 | JAVA-1
143 | Student | Cources details watched hours |  | API | Pending | 2022-12-22 | 2022-12-22 | JAVA-2
142 | Student | Cources Details |  | Frontend | Pending | 2022-12-23 | 2022-12-23 | ANGULAR-1
144 | Student | Cources details watched hours |  | Frontend | Pending | 2022-12-23 | 2022-12-23 | ANGULAR-2
145 | Student | Gratitude Msg |  | API | Pending | 2022-12-23 | 2022-12-23 | JAVA-1
147 | Student | My cource material |  | API | Pending | 2022-12-23 | 2022-12-23 | JAVA-2
146 | Student | Exclusive Msg - Reply for Guruji |  | Frontend | Pending | 2022-12-26 | 2022-12-26 | ANGULAR-1
148 | Student | My cource material |  | Frontend | Pending | 2022-12-26 | 2022-12-26 | ANGULAR-2
149 | Student | Notifications |  | API | Pending | 2022-12-26 | 2022-12-26 | JAVA-1
151 | Student | Past Cources |  | API | Pending | 2022-12-26 | 2022-12-26 | JAVA-2
150 | Student | Notifications |  | Frontend | Pending | 2022-12-27 | 2022-12-27 | ANGULAR-1
152 | Student | Past Cources |  | Frontend | Pending | 2022-12-27 | 2022-12-27 | ANGULAR-2
153 | Student | Reply from Guruji |  | API | Pending | 2022-12-27 | 2022-12-27 | JAVA-1
155 | Student | Resources |  | API | Pending | 2022-12-27 | 2022-12-27 | JAVA-2
154 | Student | Resources |  | Frontend | Pending | 2022-12-28 | 2022-12-28 | ANGULAR-1
156 | Student | Resources - sorting |  | Frontend | Pending | 2022-12-28 | 2022-12-28 | ANGULAR-2
157 | Student | Resources - sorting |  | API | Pending | 2022-12-28 | 2022-12-28 | JAVA-1
158 | Student | Status of tasks & certifications |  | Frontend | Pending | 2022-12-29 | 2022-12-29 | ANGULAR-1
159 | Student | My task certificate view |  | API | Pending | 2023-01-02 | 2023-01-02 | JAVA-2
161 | Student | View Gratitude Msg |  | API | Pending | 2023-01-02 | 2023-01-02 | JAVA-1
160 | Student | View all Gratitude Msg |  | Frontend | Pending | 2023-01-03 | 2023-01-03 | ANGULAR-2
162 | Student | View tasks |  | Frontend | Pending | 2023-01-03 | 2023-01-03 | ANGULAR-1
163 | Student | World Wide Gratitude Msg |  | API | Pending | 2023-01-03 | 2023-01-03 | JAVA-2
165 | Student | Write Gratitude msg |  | API | Pending | 2023-01-03 | 2023-01-03 | JAVA-1
164 | Student | World Wide Gratitude Msg view |  | Frontend | Pending | 2023-01-04 | 2023-01-04 | ANGULAR-2
166 | Student | All my gratitude msg view |  | Frontend | Pending | 2023-01-04 | 2023-01-04 | ANGULAR-1
167 | Student | View tasks |  | API | Pending | 2023-01-04 | 2023-01-04 | JAVA-2
169 | Student | World wide gratitude msg view |  | API | Pending | 2023-01-04 | 2023-01-04 | JAVA-1
168 | Student | World wide gratitude msg |  | Frontend | Pending | 2023-01-05 | 2023-01-05 | ANGULAR-2
170 | Student | Write World wide gratitude msg view |  | Frontend | Pending | 2023-01-05 | 2023-01-05 | ANGULAR-1
171 | Mentor | Dashboard |  | API | Pending | 2023-01-05 | 2023-01-05 | JAVA-1
173 | Mentor | Dashboard count click |  | API | Pending | 2023-01-05 | 2023-01-05 | JAVA-2
172 | Mentor | Dashboard |  | Frontend | Pending | 2023-01-06 | 2023-01-06 | ANGULAR-1
174 | Mentor | Dashboard count click |  | Frontend | Pending | 2023-01-06 | 2023-01-06 | ANGULAR-2
175 | Mentor | Total applications assign to mentor |  | API | Pending | 2023-01-06 | 2023-01-06 | JAVA-1
177 | Mentor | Active students as on the day |  | API | Pending | 2023-01-06 | 2023-01-06 | JAVA-2
176 | Mentor | Total applications assign to mentor |  | Frontend | Pending | 2023-01-09 | 2023-01-09 | ANGULAR-1
178 | Mentor | Active students as on the day |  | Frontend | Pending | 2023-01-09 | 2023-01-09 | ANGULAR-2
179 | Mentor | View student - Profile |  | API | Pending | 2023-01-09 | 2023-01-09 | JAVA-1
181 | Mentor | View student - Cources Profile |  | API | Pending | 2023-01-09 | 2023-01-09 | JAVA-2
180 | Mentor | View student - Profile |  | Frontend | Pending | 2023-01-10 | 2023-01-10 | ANGULAR-1
182 | Mentor | View student - Cources Profile |  | Frontend | Pending | 2023-01-10 | 2023-01-10 | ANGULAR-2
183 | Mentor | View student - Donations |  | API | Pending | 2023-01-10 | 2023-01-10 | JAVA-1
185 | Mentor | View student - e Purcheses |  | API | Pending | 2023-01-10 | 2023-01-10 | JAVA-2
184 | Mentor | View student - Donations |  | Frontend | Pending | 2023-01-11 | 2023-01-11 | ANGULAR-1
186 | Mentor | View student - e Purcheses |  | Frontend | Pending | 2023-01-11 | 2023-01-11 | ANGULAR-2
187 | Mentor | View student - Volintering Details |  | API | Pending | 2023-01-11 | 2023-01-11 | JAVA-1
189 | Mentor | View student - Performance report |  | API | Pending | 2023-01-11 | 2023-01-11 | JAVA-2
188 | Mentor | View student - Volintering Details |  | Frontend | Pending | 2023-01-12 | 2023-01-12 | ANGULAR-1
190 | Mentor | View student - Performance report |  | Frontend | Pending | 2023-01-12 | 2023-01-12 | ANGULAR-2
191 | Mentor | Gradtitude msg forward |  | API | Pending | 2023-01-12 | 2023-01-12 | JAVA-1
193 | Mentor | Gradtitude msg chief menter |  | API | Pending | 2023-01-12 | 2023-01-12 | JAVA-2
192 | Mentor | Gradtitude msg unread |  | Frontend | Pending | 2023-01-13 | 2023-01-13 | ANGULAR-1
194 | Mentor | Gradtitude msg informed & denied |  | Frontend | Pending | 2023-01-13 | 2023-01-13 | ANGULAR-2
195 | Mentor | Gradtitude Msg editor |  | API | Pending | 2023-01-13 | 2023-01-13 | JAVA-1
196 | Mentor | Gradtitude msg summary |  | Frontend | Pending | 2023-01-16 | 2023-01-16 | ANGULAR-1
198 | Mentor | View certificate seeker |  | Frontend | Pending | 2023-01-16 | 2023-01-16 | ANGULAR-2
197 | Mentor | View certificate seeker |  | API | Pending | 2023-01-17 | 2023-01-17 | JAVA-2
199 | Mentor | Gurudakshana paid list |  | API | Pending | 2023-01-17 | 2023-01-17 | JAVA-1
200 | Mentor | Evaluation of task assignment list |  | Frontend | Pending | 2023-01-17 | 2023-01-17 | ANGULAR-1
202 | Mentor | Graditude Msg exclusive |  | Frontend | Pending | 2023-01-17 | 2023-01-17 | ANGULAR-2
201 | Mentor | Evaluation of task assignment |  | API | Pending | 2023-01-18 | 2023-01-18 | JAVA-2
203 | Mentor | list of voliters intrested |  | API | Pending | 2023-01-18 | 2023-01-18 | JAVA-1
204 | Mentor | list of voliters intrested |  | Frontend | Pending | 2023-01-18 | 2023-01-18 | ANGULAR-1
206 | Mentor | Guruji report |  | Frontend | Pending | 2023-01-18 | 2023-01-18 | ANGULAR-2
205 | Mentor | Messgae from Guruji |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-2
207 | Mentor | Response given to chief mentor and students |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-1
208 | Chief Mentor | Dashboard |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-1
210 | Chief Mentor | Dashboared count click |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-2
209 | Chief Mentor | Dashboard |  | Frontend | Pending | 2023-01-20 | 2023-01-20 | ANGULAR-1
211 | Chief Mentor | Dashboared count click |  | Frontend | Pending | 2023-01-20 | 2023-01-20 | ANGULAR-2
212 | Chief Mentor | world wide app |  | API | Pending | 2023-01-20 | 2023-01-20 | JAVA-1
214 | Chief Mentor | My region application |  | API | Pending | 2023-01-20 | 2023-01-20 | JAVA-2
213 | Chief Mentor | world wide app |  | Frontend | Pending | 2023-01-23 | 2023-01-23 | ANGULAR-1
215 | Chief Mentor | My region application |  | Frontend | Pending | 2023-01-23 | 2023-01-23 | ANGULAR-2
216 | Chief Mentor | Manage exemptions |  | API | Pending | 2023-01-23 | 2023-01-23 | JAVA-1
218 | Chief Mentor | my mentors |  | API | Pending | 2023-01-23 | 2023-01-23 | JAVA-2
217 | Chief Mentor | Manage exemptions |  | Frontend | Pending | 2023-01-24 | 2023-01-24 | ANGULAR-1
219 | Chief Mentor | my mentors |  | Frontend | Pending | 2023-01-24 | 2023-01-24 | ANGULAR-2
220 | Chief Mentor | View student - Profile |  | API | Pending | 2023-01-24 | 2023-01-24 | JAVA-1
222 | Chief Mentor | View student - Performance details |  | API | Pending | 2023-01-24 | 2023-01-24 | JAVA-2
221 | Chief Mentor | View student - Profile |  | Frontend | Pending | 2023-01-25 | 2023-01-25 | ANGULAR-1
223 | Chief Mentor | View student - Performance details |  | Frontend | Pending | 2023-01-25 | 2023-01-25 | ANGULAR-2
224 | Chief Mentor | View student - Donations |  | API | Pending | 2023-01-25 | 2023-01-25 | JAVA-1
226 | Chief Mentor | View student - e Purcheses |  | API | Pending | 2023-01-25 | 2023-01-25 | JAVA-2
225 | Chief Mentor | View student - Donations |  | Frontend | Pending | 2023-01-27 | 2023-01-27 | ANGULAR-1
227 | Chief Mentor | View student - e Purcheses |  | Frontend | Pending | 2023-01-27 | 2023-01-27 | ANGULAR-2
228 | Chief Mentor | View student - Volintering Details |  | API | Pending | 2023-01-27 | 2023-01-27 | JAVA-1
230 | Chief Mentor | View student - Cources profile |  | API | Pending | 2023-01-27 | 2023-01-27 | JAVA-2
229 | Chief Mentor | View student - Volintering Details |  | Frontend | Pending | 2023-01-30 | 2023-01-30 | ANGULAR-1
231 | Chief Mentor | View student - Cources profile |  | Frontend | Pending | 2023-01-30 | 2023-01-30 | ANGULAR-2
232 | Chief Mentor | Gradtitude msg informed denied |  | API | Pending | 2023-01-30 | 2023-01-30 | JAVA-1
234 | Chief Mentor | Gradtitude msg - edit |  | API | Pending | 2023-01-30 | 2023-01-30 | JAVA-2
233 | Chief Mentor | Gradtitude msg - Unread |  | Frontend | Pending | 2023-01-31 | 2023-01-31 | ANGULAR-1
235 | Chief Mentor | Gradtitude msg circular msg |  | Frontend | Pending | 2023-01-31 | 2023-01-31 | ANGULAR-2
236 | Chief Mentor | Gradtitude msg -recomemded |  | API | Pending | 2023-01-31 | 2023-01-31 | JAVA-1
238 | Chief Mentor | View certificate seekar |  | API | Pending | 2023-01-31 | 2023-01-31 | JAVA-2
237 | Chief Mentor | Graditude summaryu |  | Frontend | Pending | 2023-02-01 | 2023-02-01 | ANGULAR-1
239 | Chief Mentor | View certificate seekar |  | Frontend | Pending | 2023-02-01 | 2023-02-01 | ANGULAR-2
240 | Chief Mentor | Gurudakshana seekar |  | API | Pending | 2023-02-01 | 2023-02-01 | JAVA-1
242 | Chief Mentor | Graditude msg - exclusive vn |  | API | Pending | 2023-02-01 | 2023-02-01 | JAVA-2
241 | Chief Mentor | Evalution task assignment |  | Frontend | Pending | 2023-02-02 | 2023-02-02 | ANGULAR-1
243 | Chief Mentor | list of volinters |  | Frontend | Pending | 2023-02-02 | 2023-02-02 | ANGULAR-2
244 | Chief Mentor | list of volinters |  | API | Pending | 2023-02-02 | 2023-02-02 | JAVA-1
246 | Chief Mentor | Manage exemptions |  | API | Pending | 2023-02-02 | 2023-02-02 | JAVA-2
245 | Chief Mentor | Manage exemptions |  | Frontend | Pending | 2023-02-03 | 2023-02-03 | ANGULAR-1
248 | Chief Mentor | read graditude msg with names - region |  | API | Pending | 2023-02-03 | 2023-02-03 | JAVA-1
250 | Chief Mentor | Report of automatic remove |  | API | Pending | 2023-02-03 | 2023-02-03 | JAVA-2
247 | Chief Mentor | message from guruji |  | Frontend | Pending | 2023-02-06 | 2023-02-06 | ANGULAR-2
249 | Chief Mentor | read graditude msg with names - all |  | Frontend | Pending | 2023-02-06 | 2023-02-06 | ANGULAR-1
252 | Chief Mentor | report of graditude reading |  | API | Pending | 2023-02-06 | 2023-02-06 | JAVA-1
254 | Guruji | Dashboard |  | API | Pending | 2023-02-06 | 2023-02-06 | JAVA-2
251 | Chief Mentor | Report of automatic remove |  | Frontend | Pending | 2023-02-07 | 2023-02-07 | ANGULAR-2
253 | Chief Mentor | message given to studen and mentor |  | Frontend | Pending | 2023-02-07 | 2023-02-07 | ANGULAR-1
255 | Guruji | Dashboard |  | Frontend | Pending | 2023-02-07 | 2023-02-07 | ANGULAR-2
256 | Guruji | Dashboared Cources report |  | API | Pending | 2023-02-07 | 2023-02-07 | JAVA-1
258 | Guruji | Guruji msg - exclusive vn |  | API | Pending | 2023-02-07 | 2023-02-07 | JAVA-2
257 | Guruji | Dashboared Cources report |  | Frontend | Pending | 2023-02-08 | 2023-02-08 | ANGULAR-1
259 | Guruji | Guruji msg - all students |  | Frontend | Pending | 2023-02-08 | 2023-02-08 | ANGULAR-2
260 | Guruji | Message to chief mentor |  | API | Pending | 2023-02-08 | 2023-02-08 | JAVA-1
262 | Guruji | Recommended msg |  | API | Pending | 2023-02-08 | 2023-02-08 | JAVA-2
261 | Guruji | Recommended msg list |  | Frontend | Pending | 2023-02-09 | 2023-02-09 | ANGULAR-1
263 | Guruji | Report of graditude reading of students |  | Frontend | Pending | 2023-02-09 | 2023-02-09 | ANGULAR-2
264 | Guruji | Report of graditude reading of schief mentors |  | API | Pending | 2023-02-09 | 2023-02-09 | JAVA-1
266 | Guruji | View student - Profile |  | API | Pending | 2023-02-09 | 2023-02-09 | JAVA-2
265 | Guruji | View student - Profile |  | Frontend | Pending | 2023-02-10 | 2023-02-10 | ANGULAR-1
267 | Guruji | View student - Performance details |  | Frontend | Pending | 2023-02-10 | 2023-02-10 | ANGULAR-2
268 | Guruji | View student - Performance details |  | API | Pending | 2023-02-10 | 2023-02-10 | JAVA-1
270 | Guruji | View student - Donations |  | API | Pending | 2023-02-10 | 2023-02-10 | JAVA-2
269 | Guruji | View student - Donations |  | Frontend | Pending | 2023-02-13 | 2023-02-13 | ANGULAR-1
271 | Guruji | View student - e Purcheses |  | Frontend | Pending | 2023-02-13 | 2023-02-13 | ANGULAR-2
272 | Guruji | View student - e Purcheses |  | API | Pending | 2023-02-14 | 2023-02-14 | JAVA-1
274 | Guruji | View student - Volintering Details |  | API | Pending | 2023-02-14 | 2023-02-14 | JAVA-2
273 | Guruji | View student - Volintering Details |  | Frontend | Pending | 2023-02-15 | 2023-02-15 | ANGULAR-1
275 | Guruji | View student - Cources profile |  | Frontend | Pending | 2023-02-15 | 2023-02-15 | ANGULAR-2
276 | Guruji | View student - Cources profile |  | API | Pending | 2023-02-15 | 2023-02-15 | JAVA-1
278 | Guruji | Region summary |  | API | Pending | 2023-02-15 | 2023-02-15 | JAVA-2
277 | Guruji | Region summary |  | Frontend | Pending | 2023-02-16 | 2023-02-16 | ANGULAR-1
279 | Guruji | Users |  | Frontend | Pending | 2023-02-16 | 2023-02-16 | ANGULAR-2
280 | Guruji | Users |  | API | Pending | 2023-02-16 | 2023-02-16 | JAVA-1
281 | Guruji | world wide application |  | API | Pending | 2023-02-16 | 2023-02-16 | JAVA-2
281 | Guruji | replies given to graditity admin |  | Frontend | Pending | 2023-02-17 | 2023-02-17 | ANGULAR-1
282 | Guruji | world wide application |  | Frontend | Pending | 2023-02-17 | 2023-02-17 | ANGULAR-2
283 | Gratitude-admin | Dashboard |  | API | Pending | 2023-02-20 | 2023-02-20 | JAVA-1
285 | Gratitude-admin | world wide Application |  | API | Pending | 2023-02-20 | 2023-02-20 | JAVA-2
284 | Gratitude-admin | Dashboard |  | Frontend | Pending | 2023-02-21 | 2023-02-21 | ANGULAR-1
286 | Gratitude-admin | World Wide Application |  | Frontend | Pending | 2023-02-21 | 2023-02-21 | ANGULAR-2
287 | Gratitude-admin | Number of Mentor |  | API | Pending | 2023-02-21 | 2023-02-21 | JAVA-1
289 | Gratitude-admin | World wide Application |  | API | Pending | 2023-02-21 | 2023-02-21 | JAVA-2
288 | Gratitude-admin | Number of Mentor |  | Frontend | Pending | 2023-02-22 | 2023-02-22 | ANGULAR-1
290 | Gratitude-admin | world Wide Application |  | Frontend | Pending | 2023-02-22 | 2023-02-22 | ANGULAR-2
291 | Gratitude-admin | Manage exemptions |  | API | Pending | 2023-02-22 | 2023-02-22 | JAVA-1
293 | Gratitude-admin | View-Student |  | API | Pending | 2023-02-22 | 2023-02-22 | JAVA-2
292 | Gratitude-admin | Manage exemptions |  | Frontend | Pending | 2023-02-24 | 2023-02-24 | ANGULAR-1
294 | Gratitude-admin | View-Student |  | Frontend | Pending | 2023-02-24 | 2023-02-24 | ANGULAR-2
295 | Gratitude-admin | Course-profile |  | API | Pending | 2023-02-24 | 2023-02-24 | JAVA-1
297 | Gratitude-admin | Donations management |  | API | Pending | 2023-02-24 | 2023-02-24 | JAVA-2
296 | Gratitude-admin | Course-profile |  | Frontend | Pending | 2023-02-27 | 2023-02-27 | ANGULAR-1
298 | Gratitude-admin | Donations management |  | Frontend | Pending | 2023-02-27 | 2023-02-27 | ANGULAR-2
299 | Gratitude-admin | e-purchase information |  | API | Pending | 2023-02-27 | 2023-02-27 | JAVA-1
301 | Gratitude-admin | Voulterring Details |  | API | Pending | 2023-02-27 | 2023-02-27 | JAVA-2
300 | Gratitude-admin | e-purchase information |  | Frontend | Pending | 2023-02-28 | 2023-02-28 | ANGULAR-1
302 | Gratitude-admin | Voulterring Details |  | Frontend | Pending | 2023-02-28 | 2023-02-28 | ANGULAR-2
303 | Gratitude-admin | performance-report |  | API | Pending | 2023-02-28 | 2023-02-28 | JAVA-1
305 | Gratitude-admin | Alerts-View |  | API | Pending | 2023-02-28 | 2023-02-28 | JAVA-2
304 | Gratitude-admin | performance-report |  | Frontend | Pending | 2023-03-01 | 2023-03-01 | ANGULAR-1
306 | Gratitude-admin | Alerts-View |  | Frontend | Pending | 2023-03-01 | 2023-03-01 | ANGULAR-2
307 | Gratitude-admin | Alerts |  | API | Pending | 2023-03-01 | 2023-03-01 | JAVA-1
309 | Gratitude-admin | Black List users |  | API | Pending | 2023-03-01 | 2023-03-01 | JAVA-2
308 | Gratitude-admin | Alerts |  | Frontend | Pending | 2023-03-02 | 2023-03-02 | ANGULAR-1
310 | Gratitude-admin | Black List users |  | Frontend | Pending | 2023-03-02 | 2023-03-02 | ANGULAR-2
311 | Gratitude-admin | circulation-messages |  | API | Pending | 2023-03-02 | 2023-03-02 | JAVA-1
313 | Gratitude-admin | circulation-messages -All messages |  | API | Pending | 2023-03-02 | 2023-03-02 | JAVA-2
312 | Gratitude-admin | circulation-messages |  | Frontend | Pending | 2023-03-03 | 2023-03-03 | ANGULAR-1
314 | Gratitude-admin | circulation-messages -All messages |  | Frontend | Pending | 2023-03-03 | 2023-03-03 | ANGULAR-2
315 | Gratitude-admin | Guruji-reply |  | API | Pending | 2023-03-03 | 2023-03-03 | JAVA-1
317 | Gratitude-admin | My-course-material |  | API | Pending | 2023-03-03 | 2023-03-03 | JAVA-2
316 | Gratitude-admin | Guruji-reply |  | Frontend | Pending | 2023-03-06 | 2023-03-06 | ANGULAR-1
318 | Gratitude-admin | My-course-material |  | Frontend | Pending | 2023-03-06 | 2023-03-06 | ANGULAR-2
319 | Gratitude-admin | Gratitudemessage-VN Experience |  | API | Pending | 2023-03-06 | 2023-03-06 | JAVA-1
321 | Gratitude-admin | Gratitudemessage-VN Experience -view |  | API | Pending | 2023-03-06 | 2023-03-06 | JAVA-2
320 | Gratitude-admin | Gratitudemessage-VN Experience |  | Frontend | Pending | 2023-03-07 | 2023-03-07 | ANGULAR-1
322 | Gratitude-admin | Gratitudemessage-VN Experience -view |  | Frontend | Pending | 2023-03-07 | 2023-03-07 | ANGULAR-2
323 | Gratitude-admin | Glimpes |  | API | Pending | 2023-03-07 | 2023-03-07 | JAVA-1
325 | Gratitude-admin | message from Guruji |  | API | Pending | 2023-03-07 | 2023-03-07 | JAVA-2
324 | Gratitude-admin | Glimpes |  | Frontend | Pending | 2023-03-08 | 2023-03-08 | ANGULAR-1
326 | Gratitude-admin | message from Guruji |  | Frontend | Pending | 2023-03-08 | 2023-03-08 | ANGULAR-2
327 | Gratitude-admin | Notifications |  | API | Pending | 2023-03-08 | 2023-03-08 | JAVA-1
329 | Gratitude-admin | Parameters |  | API | Pending | 2023-03-08 | 2023-03-08 | JAVA-2
328 | Gratitude-admin | Notifications |  | Frontend | Pending | 2023-03-09 | 2023-03-09 | ANGULAR-1
330 | Gratitude-admin | Parameters |  | Frontend | Pending | 2023-03-09 | 2023-03-09 | ANGULAR-2
331 | Gratitude-admin | Recommended-messages |  | API | Pending | 2023-03-09 | 2023-03-09 | JAVA-1
333 | Gratitude-admin | Recommended-messages All-messages |  | API | Pending | 2023-03-09 | 2023-03-09 | JAVA-2
332 | Gratitude-admin | Recommended-messages |  | Frontend | Pending | 2023-03-10 | 2023-03-10 | ANGULAR-1
334 | Gratitude-admin | Recommended-messages All-messages |  | Frontend | Pending | 2023-03-10 | 2023-03-10 | ANGULAR-2
335 | Gratitude-admin | report of replies of guruji |  | API | Pending | 2023-03-10 | 2023-03-10 | JAVA-1
337 | Gratitude-admin | summary |  | API | Pending | 2023-03-10 | 2023-03-10 | JAVA-2
336 | Gratitude-admin | report of replies of guruji |  | Frontend | Pending | 2023-03-13 | 2023-03-13 | ANGULAR-1
338 | Gratitude-admin | summary |  | Frontend | Pending | 2023-03-13 | 2023-03-13 | ANGULAR-2
339 | Gratitude-admin | Task Assignment |  | API | Pending | 2023-03-13 | 2023-03-13 | JAVA-1
341 | Gratitude-admin | Create Task |  | API | Pending | 2023-03-13 | 2023-03-13 | JAVA-2
340 | Gratitude-admin | Task Assignment |  | Frontend | Pending | 2023-03-14 | 2023-03-14 | ANGULAR-1
342 | Gratitude-admin | Create Task |  | Frontend | Pending | 2023-03-14 | 2023-03-14 | ANGULAR-2
18 | Admin | World wide applications | Sumukesh | API | Open |  |  | JAVA-1
19 | Admin | World wide applications | Ajith R | Frontend | Open |  |  | ANGULAR-1
343 | QA | SIT |  |  | Pending
344 | QA | UAT1 |  |  | Pending
345 | QA | UAT2 |  |  | Pending
346 | QA | Go Live |  |  | Pending

## admin all tables
m_course_category
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_course_category | catergory_id | primary-key | INT | 10
2 | ADMIN | m_course_category | catergory_name |  | Varchar | 55 | (Student,Admin,Mentor,chief-mentor,mentor,guruji)
3 | ADMIN | m_course_category | created-date |  | Date
4 | ADMIN | m_course_category | created_by |  | Varchar | 55
5 | ADMIN | m_course_category | updated_date |  | date
6 | ADMIN | m_course_category | updated_by |  | Varchar | 55
7 | ADMIN | m_course_category | is_active |  | Varchar | 10
m_course
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_courses | course_id | primary-key | INT | 10
2 | ADMIN | m_courses | course_name |  | Varchar | 55
3 | ADMIN | m_courses | course_type |  | Varchar | 55
4 | ADMIN | m_courses | section |  | section | 55
5 | ADMIN | m_courses | course_duration |  | int | 55
6 | ADMIN | m_courses | Verficication_required |  | Varchar | 10 | Verfication(yes or No)
7 | ADMIN | m_courses | created-date |  | Date
8 | ADMIN | m_courses | created_by |  | Varchar | 55
9 | ADMIN | m_courses | updated_date |  | date
10 | ADMIN | m_courses | updated_by |  | Varchar | 55
11 | ADMIN | m_courses | is_active |  | Varchar | 10
Table_name: course_media_files
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | course_media_files | Id | primary-key | int | 55
2 | ADMIN | course_media_files | courses_Id |  | int | 55
3 | ADMIN | course_media_files | courses_type |  | varchar | 255 | VideoType(short,liveclasses,pratice)
4 | ADMIN | course_media_files | section |  | varchar | 255
5 | ADMIN | course_media_files | course_duration |  | int | 55
6 | ADMIN | course_media_files | verfication |  | varchar | 10 | Verfication(yes or No)
7 | ADMIN | course_media_files | created-date |  | Date
8 | ADMIN | course_media_files | created_by |  | Varchar | 55
9 | ADMIN | course_media_files | updated_date |  | date
10 | ADMIN | course_media_files | updated_by |  | Varchar | 55
11 | ADMIN | course_media_files | is_active |  | Varchar | 10
m_exceptions
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_exceptions | exception_id | primary-key | int | 10
2 | ADMIN | m_exceptions | exception_Desc |  |  | 255
3 | ADMIN | m_exceptions | created-date |  | Date
4 | ADMIN | m_exceptions | created_by |  | Varchar | 55
5 | ADMIN | m_exceptions | updated_date |  | date
6 | ADMIN | m_exceptions | updated_by |  | Varchar | 55
7 | ADMIN | m_exceptions | is_active |  | Varchar | 10
course_exceptions
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | course_exceptions | course_id | primary-key | int | 10
2 | ADMIN | course_exceptions | exceptions_id | ForigenKey(m_exception) | int | 10
3 | ADMIN | course_exceptions | status |  | varchar | 255
|  |  | created-date |  | Date
|  |  | created_by |  | Varchar | 55
|  |  | updated_date |  | date
|  |  | updated_by |  | Varchar | 55
|  |  | is_active |  | Varchar | 10
table_name: m_student_status
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_student_status | student_status_Id | primary-key | int | 10
2 | ADMIN | m_student_status | student_status |  | varchar
| ADMIN | m_student_status | created-date |  | Date |  | active ,inactive,block,
| ADMIN | m_student_status | created_by |  | Varchar | 55
| ADMIN | m_student_status | updated_date |  | date
| ADMIN | m_student_status | updated_by |  | Varchar | 55
| ADMIN | m_student_status | is_active |  | Varchar | 10
student_course_assignement
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | student_course_assignement | id | primary-key | int | 55
2 | ADMIN | student_course_assignement | student_id |  | int | 55
3 | ADMIN | student_course_assignement | course_Id | ForigenKey(m_exception) | int | 55
4 | ADMIN | student_course_assignement | batch_Id |  | int | 55
5 | ADMIN | student_course_assignement | created-date |  | Date
6 | ADMIN | student_course_assignement | created_by |  | Varchar | 55
7 | ADMIN | student_course_assignement | updated_date |  | date
8 | ADMIN | student_course_assignement | updated_by |  | Varchar | 55
9 | ADMIN | student_course_assignement | is_active |  | Varchar | 10
table_name : student_reporting_mapping
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | student_reporting_mapping | id | primary-key | int | 55
2 | ADMIN | student_reporting_mapping | Admin_id |  | int | 55
3 | ADMIN | student_reporting_mapping | student_id |  | int | 55
4 | ADMIN | student_reporting_mapping | cheif_mentorId |  | int | 55
5 | ADMIN | student_reporting_mapping | mentor_id |  | int | 55
6 | ADMIN | student_reporting_mapping | guruji_id |  | int | 55
7 | ADMIN | student_reporting_mapping | created-date |  | Date
8 | ADMIN | student_reporting_mapping | created_by |  | Varchar | 55
9 | ADMIN | student_reporting_mapping | updated_date |  | date
10 | ADMIN | student_reporting_mapping | updated_by |  | Varchar | 55
11 | ADMIN | student_reporting_mapping | is_active |  | Varchar | 10
table: registration
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | registration | registration_id | primary-key | int | 10
2 | ADMIN | registration | registration_email |  | varchar | 255
3 | ADMIN | registration | registration_name |  | varchar | 55
4 | ADMIN | registration | registration_profession | ForigenKey(profession) | varchar | 10
5 | ADMIN | registration | registration_gender_id | ForigenKey(gender) | int | 10
6 | ADMIN | registration | registration_qualification_id | ForigenKey(qualification) | int | 10
7 | ADMIN | registration | created-date |  | Date
8 | ADMIN | registration | created_by |  | Varchar | 55
9 | ADMIN | registration | updated_date |  | date
10 | ADMIN | registration | updated_by |  | Varchar | 55
11 | ADMIN | registration | is_active |  | Varchar | 10
tablename :profession
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | profession | profession_id |  | int | 10
2 | ADMIN | profession | profession_name | primary-key | varchar | 155
3 | ADMIN | profession | created-date |  | Date
4 | ADMIN | profession | created_by |  | Varchar | 55
5 | ADMIN | profession | updated_date |  | date
6 | ADMIN | profession | updated_by |  | Varchar | 55
7 | ADMIN | profession | is_active |  | Varchar | 10
Gender
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | Gender | gender_id |  | int | 10
2 | ADMIN | Gender | gender_type | primary-key | varchar | 155
3 | ADMIN | Gender | created-date |  | Date
4 | ADMIN | Gender | created_by |  | Varchar | 55
5 | ADMIN | Gender | updated_date |  | date
6 | ADMIN | Gender | updated_by |  | Varchar | 55
7 | ADMIN | Gender | is_active |  | Varchar | 10
table_name:qulification
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | qualification | qualificaation_id |  | int | 10
2 | ADMIN | qualification | qualificaation_name | primary-key | varchar | 155
3 | ADMIN | qualification | created-date |  | Date
4 | ADMIN | qualification | created_by |  | Varchar | 55
5 | ADMIN | qualification | updated_date |  | date
6 | ADMIN | qualification | updated_by |  | Varchar | 55
7 | ADMIN | qualification | is_active |  | Varchar | 10
table_name:Admission_status
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | Admission_status | Admission_id | primary-key | int | 10
2 | ADMIN | Admission_status | Admission_status |  | varchar | 155
3 | ADMIN | Admission_status | created-date |  | Date
4 | ADMIN | Admission_status | created_by |  | Varchar | 55
5 | ADMIN | Admission_status | updated_date |  | date
6 | ADMIN | Admission_status | updated_by |  | Varchar | 55
7 | ADMIN | Admission_status | is_active |  | Varchar | 10
completion_status
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | completion_status | completion_id | primary-key | int | 10
2 | ADMIN | completion_status | completion_name |  | varchar | 155 | completed,certfied,removed
3 | ADMIN | completion_status | created-date |  | Date
4 | ADMIN | completion_status | created_by |  | Varchar | 55
5 | ADMIN | completion_status | updated_date |  | date
6 | ADMIN | completion_status | updated_by |  | Varchar | 55
7 | ADMIN | completion_status | is_active |  | Varchar | 10
tablename:perfromace_grading
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | perfromace_grading | grading_Id | primary-key
2 | ADMIN | perfromace_grading | performance_name |  |  |  | good,poor,average
3 | ADMIN | perfromace_grading | created-date |  | Date
4 | ADMIN | perfromace_grading | created_by |  | Varchar | 55
5 | ADMIN | perfromace_grading | updated_date |  | date
6 | ADMIN | perfromace_grading | updated_by |  | Varchar | 55
7 | ADMIN | perfromace_grading | is_active |  | Varchar | 10
table_name:m_course_perfromance_rating
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_course_perfromance_rating | rating_id | primary-key
2 | ADMIN | m_course_perfromance_rating | course_Id | forgien-Key(m_courses)
3 | ADMIN | m_course_perfromance_rating | perfromance_Id | forgien-Key(performance_mointering)
4 | ADMIN | m_course_perfromance_rating | grading_Id | grading_Id(perfromace_grading)
3 | ADMIN | m_course_perfromance_rating | created-date |  | Date
4 | ADMIN | m_course_perfromance_rating | created_by |  | Varchar | 55
5 | ADMIN | m_course_perfromance_rating | updated_date |  | date
6 | ADMIN | m_course_perfromance_rating | updated_by |  | Varchar | 55
7 | ADMIN | m_course_perfromance_rating | is_active |  | Varchar | 10
table_name:student_pratice_session
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | student_pratice_session | Id | primary-key | int | 10
2 | ADMIN | student_pratice_session | student_id | forgien_key(student_course_assignement) | int | 10
3 | ADMIN | student_pratice_session | course_id | forgien-Key(m_courses) | int | 10
4 | ADMIN | student_pratice_session | date |  | Date
3 | ADMIN | student_pratice_session | Attended_duration |  | Date
4 | ADMIN | student_pratice_session | percentage_completion |  | int | 10
5 | ADMIN | student_pratice_session | created-date |  | Date
6 | ADMIN | student_pratice_session | created_by |  | Varchar | 55
7 | ADMIN | student_pratice_session | updated_date |  | date
8 | ADMIN | student_pratice_session | updated_by |  | Varchar | 55
9 | ADMIN | student_pratice_session | is_active |  | Varchar | 10
table_name:alert
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | alert | id | primary-key | int | 10
2 | ADMIN | alert | category_id | forigenkey(M_course_category)
3 | ADMIN | alert | alert_desc
4 | ADMIN | alert | startdate
5 | ADMIN | alert | enddate
6 | ADMIN | alert | file_name
7 | ADMIN | alert | created-date |  | Date
8 | ADMIN | alert | created_by |  | Varchar | 55
9 | ADMIN | alert | updated_date |  | date
10 | ADMIN | alert | updated_by |  | Varchar | 55
11 | ADMIN | alert | is_active |  | Varchar | 10
table_name:audio_category
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | audio_category | id | primary-key | int | 10
2 | ADMIN | audio_category | aduio_name |  | Varchar
3 | ADMIN | audio_category | audio_category |  | Varchar
4 | ADMIN | audio_category | created-date |  | Date
5 | ADMIN | audio_category | created_by |  | Varchar | 55
6 | ADMIN | audio_category | updated_date |  | date
7 | ADMIN | audio_category | updated_by |  | Varchar | 55
8 | ADMIN | audio_category | is_active |  | Varchar | 10
tablename:audio_management
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | audio_management | id | primary-key | int | 10
2 | ADMIN | audio_management | course_id | forigen_key | int | 10
3 | ADMIN | audio_management | audio_category_id |  | int | 10
4 | ADMIN | audio_management | upload_category |  | Varchar | 55
5 | ADMIN | audio_management | audio_type |  | Varchar | 55
6 | ADMIN | audio_management | audio_title |  | Varchar | 55
7 | ADMIN | audio_management | audio_desc |  | Varchar | 55
8 | ADMIN | audio_management | audio_duration |  | int | 10
9 | ADMIN | audio_management | metakey |  | Varchar | 55
10 | ADMIN | audio_management | created-date |  | Date
11 | ADMIN | audio_management | created_by |  | Varchar | 55
12 | ADMIN | audio_management | updated_date |  | date
13 | ADMIN | audio_management | updated_by |  | Varchar | 55
14 | ADMIN | audio_management | is_active |  | Varchar | 10
tablename:banner
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | banner | id | primary-key | int
2 | ADMIN | banner | banner_type |  | Varchar
3 | ADMIN | banner | title |  | Varchar
4 | ADMIN | banner | desc |  | Varchar
5 | ADMIN | banner | date |  | date
6 | ADMIN | banner | created-date |  | Date
7 | ADMIN | banner | created_by |  | Varchar | 55
8 | ADMIN | banner | updated_date |  | date
9 | ADMIN | banner | updated_by |  | Varchar | 55
10 | ADMIN | banner | is_active |  | Varchar | 10
tablename:course_material_category
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | course_material_category | id | primary-key | id
2 | ADMIN | course_material_category | category_name | forigen_key | Varchar |  | (techinical,scentific,special/day)
3 | ADMIN | course_material_category | created-date |  | Date
4 | ADMIN | course_material_category | created_by |  | Varchar | 55
5 | ADMIN | course_material_category | updated_date |  | date
6 | ADMIN | course_material_category | updated_by |  | Varchar | 55
7 | ADMIN | course_material_category | is_active |  | Varchar | 10
tablename:notification
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | notification | id | primary-key | int
2 | ADMIN | notification | category_id | forigen_key | int
3 | ADMIN | notification | noticfication_title |  | Varchar
4 | ADMIN | notification | file_name |  | Varchar
5 | ADMIN | notification | noticfication_desc |  | Varchar
6 | ADMIN | notification | created-date |  | Date
7 | ADMIN | notification | created_by |  | Varchar | 55
8 | ADMIN | notification | updated_date |  | date
9 | ADMIN | notification | updated_by |  | Varchar | 55
10 | ADMIN | notification | is_active |  | Varchar | 10
Roles
S.No | Module | sub-Module | parameter | parameterDetails | length
1 | Admin | Roles | role_id | id | 55
2 | Admin | Roles | role_name | varchar | 55
6 | ADMIN | notification | created-date |  | Date
7 | ADMIN | notification | created_by |  | Varchar | 55
8 | ADMIN | notification | updated_date |  | date
9 | ADMIN | notification | updated_by |  | Varchar | 55
10 | ADMIN | notification | is_active |  | Varchar | 10
tablename:users
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | users | user_id
2 | ADMIN | users | user_name | primary_key
3 | ADMIN | users | role_id
4 | ADMIN | users | password
5 | ADMIN | users | created-date |  | Date
6 | ADMIN | users | created_by |  | Varchar | 55
7 | ADMIN | users | updated_date |  | date
8 | ADMIN | users | updated_by |  | Varchar | 55
9 | ADMIN | users | is_active |  | Varchar | 10