## Overview
Task/Activity | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Requirement Analysis & Solution Design | bar: 2022-10-01
Application Development | bar: 2022-11-01 to 2023-02-01
SIT | bar: 2023-01-01 to 2023-02-01
UAT 1 | bar: 2023-02-01
UAT 2 | bar: 2023-03-01
Deployment | bar: 2023-03-01

## Detailed Plan
S.No | Module | Task Details | Member | Frontend/API | Status | Start Date | End Date | Resource | Remarks
2 | Admin | Role | Sumukesh | API | Completed | 2022-10-31 | 2022-10-31 | JAVA-1
4 | Admin | Registration | Sumukesh | API | Completed | 2022-10-31 | 2022-10-31 | JAVA-2
6 | Admin | Role Permission | Sumukesh | API | Completed | 2022-11-01 | 2022-11-01 | JAVA-1
8 | Admin | Menu | Sumukesh | API | Completed | 2022-11-01 | 2022-11-01 | JAVA-2
3 | Admin | Role | Shekar | Frontend | Completed | 2022-11-02 | 2022-11-02 | ANGULAR-1
5 | Admin | Registration | Shekar | Frontend | Completed | 2022-11-02 | 2022-11-02 | ANGULAR-2
10 | Admin | Sub-Menu | Sumukesh | API | Completed | 2022-11-02 | 2022-11-02 | JAVA-1
12 | Admin | User | Sumukesh | API | Completed | 2022-11-02 | 2022-11-02 | JAVA-2
7 | Admin | Rolepermission | Shekar | Frontend | Completed | 2022-11-03 | 2022-11-03 | ANGULAR-1
9 | Admin | Menu | Shekar | Frontend | Completed | 2022-11-03 | 2022-11-03 | ANGULAR-2
14 | Admin | DashBoard - Course Resport | Sumukesh | API | Completed | 2022-11-16 | 2022-11-03 | JAVA-1
16 | Admin | DashBoard - OverallReport | Sumukesh | API | Completed | 2022-11-16 | 2022-11-03 | JAVA-2
11 | Admin | Sub-menu | Shekar | Frontend | Completed | 2022-11-04 | 2022-11-04 | ANGULAR-1
13 | Admin | User | Shekar | Frontend | Completed | 2022-11-04 | 2022-11-04 | ANGULAR-2
15 | Admin | DashBoard - Course Resport | Shekar | Frontend | Completed | 2022-11-07 | 2022-11-07 | ANGULAR-1
17 | Admin | DashBoard - OverallReport | Shekar | Frontend | Completed | 2022-11-07 | 2022-11-07 | ANGULAR-2
22 | Admin | View student | Sumukesh | API | In Progress | 2022-11-16 | 2022-11-07 | JAVA-1
24 | Admin | View Student - Course Profile | Sumukesh | API | In Progress | 2022-11-16 | 2022-11-07 | JAVA-2
26 | Admin | View Student -Donation | Praneeth | API | In Progress | 2022-11-16 | 2022-11-08 | JAVA-1
28 | Admin | View Student- e-purchases Information | Praneeth | API | In Progress | 2022-11-16 | 2022-11-08 | JAVA-2
23 | Admin | View student | Shekar | Frontend | Completed | 2022-11-09 | 2022-11-09 | ANGULAR-1
30 | Admin | View Student - Add Purchases | Sumukesh | API | In Progress | 2022-11-16 | 2022-11-09 | JAVA-1
32 | Admin | View Student- Volunteering details | Sumukesh | API | In Progress | 2022-11-16 | 2022-11-09 | JAVA-2
1 | Common | Analysis & Design (DB, Application, UI) |  |  | In Progress | 2022-10-13 | 2022-11-10
27 | Admin | View Student -Donation | Shekar | Frontend | Completed | 2022-11-10 | 2022-11-10 | ANGULAR-1
29 | Admin | View Student- e-purchases Information | Shekar | Frontend | Completed | 2022-11-10 | 2022-11-10 | ANGULAR-2
34 | Admin | View Student -Add Volunteer | Praneeth | API | In Progress | 2022-11-16 | 2022-11-10 | JAVA-1
36 | Admin | View student - Permonce report | Sumukesh | API | In Progress | 2022-11-16 | 2022-11-10 | JAVA-2
37 | Admin | Alerts | Ajith R | Frontend | Completed | 2022-11-14 | 2022-11-14 | ANGULAR-2 | Completed But yet to be commited
25 | Admin | View Student - Course Profile | Shekar | Frontend | In Progress | 2022-11-09 | 2022-11-16 | ANGULAR-2
31 | Admin | View Student - Add Purchases | Shekar | Frontend | Completed | 2022-11-11 | 2022-11-16 | ANGULAR-1
33 | Admin | View Student- Volunteering details | Shekar | Frontend | Completed | 2022-11-11 | 2022-11-16 | ANGULAR-2
35 | Admin | View student - Permonce report | Shekar | Frontend | Completed | 2022-11-14 | 2022-11-16 | ANGULAR-1
39 | Admin | Audio Management - Audio Dharanas | Ajith R | Frontend | Completed | 2022-11-15 | 2022-11-16 | ANGULAR-1 | Completed But yet to be commited
41 | Admin | Banners | Ajith R | Frontend | Completed | 2022-11-15 | 2022-11-16 | ANGULAR-2 | Completed But yet to be commited
43 | Admin | Add Banner | Ajith Kumar | Frontend | Completed | 2022-11-16 | 2022-11-16 | ANGULAR-1
38 | Admin | Alerts | Praneeth | API | In Progress | 2022-11-11 | 2022-11-17 | JAVA-1
40 | Admin | Audio Management - Audio Dharanas | Sumukesh | API | Pending | 2022-11-11 | 2022-11-17 | JAVA-2
42 | Admin | Banners | Praneeth | API | In Progress | 2022-11-14 | 2022-11-17 | JAVA-1
44 | Admin | Add Banner | Sumukesh | API | Pending | 2022-11-14 | 2022-11-17 | JAVA-2
45 | Admin | Black List users | Ajith Kumar | Frontend | Completed | 2022-11-16 | 2022-11-17 | ANGULAR-2
47 | Admin | Class Media Update | Ajith R | Frontend | Completed | 2022-11-17 | 2022-11-17 | ANGULAR-1 | Completed But yet to be commited
49 | Admin | Course Media Live Class | Ajith R | Frontend | Completed | 2022-11-17 | 2022-11-17 | ANGULAR-2 | Completed But yet to be commited
46 | Admin | Black List users | Praneeth | API | In Progress | 2022-11-15 | 2022-11-18 | JAVA-1
48 | Admin | Class Media Update | Sumukesh | API | Pending | 2022-11-15 | 2022-11-18 | JAVA-2
50 | Admin | Course Media Live Class | Praneeth | API | In Progress | 2022-11-16 | 2022-11-18 | JAVA-1
51 | Admin | Course Media Practice sessions | Ajith Kumar | Frontend | Completed | 2022-11-18 | 2022-11-18 | ANGULAR-1
52 | Admin | Course Media Practice sessions | Sumukesh | API | Pending | 2022-11-16 | 2022-11-18 | JAVA-2
53 | Admin | Courses | Ajith Kumar | Frontend | Completed | 2022-11-18 | 2022-11-18 | ANGULAR-2
54 | Admin | Courses | Praneeth | API | In Progress | 2022-11-17 | 2022-11-21 | JAVA-1
55 | Admin | Add Course / View Course details | Ajith R | Frontend | Completed | 2022-11-21 | 2022-11-21 | ANGULAR-1
56 | Admin | Add Course / View Course details | Sumukesh | API | Pending | 2022-11-17 | 2022-11-21 | JAVA-2
57 | Admin | Create a Practice Library | Karthik | Frontend | Completed | 2022-11-21 | 2022-11-21 | ANGULAR-2
58 | Admin | Create a Practice Library | Praneeth | API | Pending | 2022-11-18 | 2022-11-21 | JAVA-1
60 | Admin | List of Practice library | Sumukesh | API | Pending | 2022-11-18 | 2022-11-21 | JAVA-2
62 | Admin | Create scripctures |  | API | Pending | 2022-11-21 | 2022-11-21 | JAVA-1
64 | Admin | Donations management |  | API | Pending | 2022-11-21 | 2022-11-21 | JAVA-2
66 | Admin | View details |  | API | Pending | 2022-11-21 | 2022-11-21 | JAVA-1
59 | Admin | List of Practice library | Ajith Kumar | Frontend | Completed | 2022-11-22 | 2022-11-22 | ANGULAR-1
61 | Admin | Create scripctures | Karthik | Frontend | Completed | 2022-11-22 | 2022-11-22 | ANGULAR-2
68 | Admin | Hide Menu Option |  | API | Pending | 2022-11-22 | 2022-11-22 | JAVA-2
70 | Admin | Map user to course |  | API | Pending | 2022-11-22 | 2022-11-22 | JAVA-1
63 | Admin | Donations management | Ajith Kumar | Frontend | In Progress | 2022-11-23 | 2022-11-23 | ANGULAR-1
65 | Admin | View details |  | Frontend | Pending | 2022-11-23 | 2022-11-23 | ANGULAR-2
72 | Admin | Members |  | API | Pending | 2022-11-23 | 2022-11-23 | JAVA-2
74 | Admin | Mentor mapping |  | API | Pending | 2022-11-23 | 2022-11-23 | JAVA-1
67 | Admin | Hide Menu Option |  | Frontend | Pending | 2022-11-24 | 2022-11-24 | ANGULAR-1
69 | Admin | Map user to course |  | Frontend | Pending | 2022-11-24 | 2022-11-24 | ANGULAR-2
76 | Admin | My Course Metrials |  | API | Pending | 2022-11-24 | 2022-11-24 | JAVA-2
78 | Admin | Notifications |  | API | Pending | 2022-11-24 | 2022-11-24 | JAVA-1
71 | Admin | Members |  | Frontend | Pending | 2022-11-25 | 2022-11-25 | ANGULAR-1
73 | Admin | Mentor mapping |  | Frontend | Pending | 2022-11-25 | 2022-11-25 | ANGULAR-2
75 | Admin | My Course Metrials |  | Frontend | Pending | 2022-11-28 | 2022-11-28 | ANGULAR-1
77 | Admin | Notifications |  | Frontend | Pending | 2022-11-28 | 2022-11-28 | ANGULAR-2
80 | Admin | Online Exams |  | API | Pending | 2022-11-28 | 2022-11-28 | JAVA-2
82 | Admin | Pages1 |  | API | Pending | 2022-11-28 | 2022-11-28 | JAVA-1
79 | Admin | Online Exams |  | Frontend | Pending | 2022-11-29 | 2022-11-29 | ANGULAR-1
81 | Admin | Pages1 |  | Frontend | Pending | 2022-11-29 | 2022-11-29 | ANGULAR-2
84 | Admin | Pages2 |  | API | Pending | 2022-11-29 | 2022-11-29 | JAVA-2
86 | Admin | Parameters |  | API | Pending | 2022-11-29 | 2022-11-29 | JAVA-1
83 | Admin | Pages2 |  | Frontend | Pending | 2022-11-30 | 2022-11-30 | ANGULAR-1
85 | Admin | Parameters |  | Frontend | Pending | 2022-11-30 | 2022-11-30 | ANGULAR-2
88 | Admin | pearls of wisdom |  | API | Pending | 2022-11-30 | 2022-11-30 | JAVA-2
90 | Admin | Photo gallery |  | API | Pending | 2022-11-30 | 2022-11-30 | JAVA-1
87 | Admin | pearls of wisdom |  | Frontend | Pending | 2022-12-01 | 2022-12-01 | ANGULAR-1
89 | Admin | Photo gallery |  | Frontend | Pending | 2022-12-01 | 2022-12-01 | ANGULAR-2
92 | Admin | Upload image to gallery |  | API | Pending | 2022-12-01 | 2022-12-01 | JAVA-2
94 | Admin | Create gallery |  | API | Pending | 2022-12-01 | 2022-12-01 | JAVA-1
91 | Admin | Upload image to gallery |  | Frontend | Pending | 2022-12-02 | 2022-12-02 | ANGULAR-1
93 | Admin | Create gallery |  | Frontend | Pending | 2022-12-02 | 2022-12-02 | ANGULAR-2
96 | Admin | Regions Creation |  | API | Pending | 2022-12-02 | 2022-12-02 | JAVA-2
98 | Admin | Mapping regions to Chief mentor |  | API | Pending | 2022-12-02 | 2022-12-02 | JAVA-1
95 | Admin | Regions Creation |  | Frontend | Pending | 2022-12-05 | 2022-12-05 | ANGULAR-1
97 | Admin | Mapping regions to Chief mentor |  | Frontend | Pending | 2022-12-05 | 2022-12-05 | ANGULAR-2
100 | Admin | Chief metor mapping |  | API | Pending | 2022-12-05 | 2022-12-05 | JAVA-2
102 | Admin | Task Assignment |  | API | Pending | 2022-12-05 | 2022-12-05 | JAVA-1
99 | Admin | Chief metor mapping |  | Frontend | Pending | 2022-12-06 | 2022-12-06 | ANGULAR-1
101 | Admin | Task Assignment |  | Frontend | Pending | 2022-12-06 | 2022-12-06 | ANGULAR-2
104 | Admin | Create Task |  | API | Pending | 2022-12-06 | 2022-12-06 | JAVA-2
106 | Admin | Testimonials |  | API | Pending | 2022-12-06 | 2022-12-06 | JAVA-1
103 | Admin | Create Task |  | Frontend | Pending | 2022-12-07 | 2022-12-07 | ANGULAR-1
105 | Admin | Testimonials |  | Frontend | Pending | 2022-12-07 | 2022-12-07 | ANGULAR-2
108 | Admin | Add Testimonial |  | API | Pending | 2022-12-07 | 2022-12-07 | JAVA-2
110 | Admin | Users - Search Filter |  | API | Pending | 2022-12-07 | 2022-12-07 | JAVA-1
107 | Admin | Add Testimonial |  | Frontend | Pending | 2022-12-08 | 2022-12-08 | ANGULAR-1
109 | Admin | Users - Search Filter |  | Frontend | Pending | 2022-12-08 | 2022-12-08 | ANGULAR-2
112 | Admin | Users - Find suspicious users |  | API | Pending | 2022-12-08 | 2022-12-08 | JAVA-2
114 | Admin | create album for videos |  | API | Pending | 2022-12-08 | 2022-12-08 | JAVA-1
111 | Admin | Users - Find suspicious users |  | Frontend | Pending | 2022-12-09 | 2022-12-09 | ANGULAR-1
116 | Admin | Add videos for gallery page |  | API | Pending | 2022-12-09 | 2022-12-09 | JAVA-2
118 | Admin | Video gallery1 |  | API | Pending | 2022-12-09 | 2022-12-09 | JAVA-1
113 | Admin | create album for videos |  | Frontend | Pending | 2022-12-12 | 2022-12-12 | ANGULAR-2
115 | Admin | Add videos for gallery page |  | Frontend | Pending | 2022-12-12 | 2022-12-12 | ANGULAR-1
120 | Admin | Video gallery2 |  | API | Pending | 2022-12-12 | 2022-12-12 | JAVA-2
122 | Admin | Hide Options (hide some menu options like retreat and courses) for few some students or multiple students |  | API | Pending | 2022-12-12 | 2022-12-12 | JAVA-1
117 | Admin | Video gallery1 |  | Frontend | Pending | 2022-12-13 | 2022-12-13 | ANGULAR-2
119 | Admin | Video gallery2 |  | Frontend | Pending | 2022-12-13 | 2022-12-13 | ANGULAR-1
124 | Admin | Access controls - worldwide aplications not visible for few chief Mentors |  | API | Pending | 2022-12-13 | 2022-12-13 | JAVA-2
121 | Admin | Hide Options (hide some menu options like retreat and courses) for few some students or multiple students |  | Frontend | Pending | 2022-12-14 | 2022-12-14 | ANGULAR-2
123 | Admin | Access controls - worldwide aplications not visible for few chief Mentors |  | Frontend | Pending | 2022-12-14 | 2022-12-14 | ANGULAR-1
125 | Admin | Bulk upload option whereever applicable |  | Frontend | Pending | 2022-12-16 | 2022-12-16 | ANGULAR-2
127 | Admin | Automatic allocation of mentor - defining gratitude day for mentor and chief mentor (mapping) |  | Frontend | Pending | 2022-12-16 | 2022-12-16 | ANGULAR-1
126 | Admin | Bulk upload option whereever applicable |  | API | Pending | 2022-12-19 | 2022-12-19 | JAVA-1
128 | Admin | Automatic allocation of mentor - defining gratitude day for mentor and chief mentor (mapping) |  | API | Pending | 2022-12-19 | 2022-12-19 | JAVA-2
129 | Admin | Maximum view of lists n every page |  | Frontend | Pending | 2022-12-19 | 2022-12-19 | ANGULAR-2
131 | Admin | Website Managemennt: gallary management and video management |  | Frontend | Pending | 2022-12-19 | 2022-12-19 | ANGULAR-1
130 | Admin | Maximum view of lists n every page |  | API | Pending | 2022-12-20 | 2022-12-20 | JAVA-1
132 | Admin | Website Managemennt: gallary management and video management |  | API | Pending | 2022-12-20 | 2022-12-20 | JAVA-2
133 | Admin | Free enrollment or Paid Enrollment option for student to particular course |  | Frontend | Pending | 2022-12-20 | 2022-12-20 | ANGULAR-2
135 | Admin | Exceptional registrations in the mid of the course by Admin |  | Frontend | Pending | 2022-12-20 | 2022-12-20 | ANGULAR-1
134 | Admin | Free enrollment or Paid Enrollment option for student to particular course |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-1
136 | Admin | Exceptional registrations in the mid of the course by Admin |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-2
20 | Admin | Manage Exemptions |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-2
21 | Admin | Manage Exemptions |  | Frontend | Pending | 2022-12-21 | 2022-12-21 | ANGULAR-2
137 | Student | Dashboard |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-1
139 | Student | Class |  | API | Pending | 2022-12-21 | 2022-12-21 | JAVA-2
138 | Student | Dashboard |  | Frontend | Pending | 2022-12-22 | 2022-12-22 | ANGULAR-1
140 | Student | Class |  | Frontend | Pending | 2022-12-22 | 2022-12-22 | ANGULAR-2
141 | Student | Cources Details |  | API | Pending | 2022-12-22 | 2022-12-22 | JAVA-1
143 | Student | Cources details watched hours |  | API | Pending | 2022-12-22 | 2022-12-22 | JAVA-2
142 | Student | Cources Details |  | Frontend | Pending | 2022-12-23 | 2022-12-23 | ANGULAR-1
144 | Student | Cources details watched hours |  | Frontend | Pending | 2022-12-23 | 2022-12-23 | ANGULAR-2
145 | Student | Gratitude Msg |  | API | Pending | 2022-12-23 | 2022-12-23 | JAVA-1
147 | Student | My cource material |  | API | Pending | 2022-12-23 | 2022-12-23 | JAVA-2
146 | Student | Exclusive Msg - Reply for Guruji |  | Frontend | Pending | 2022-12-26 | 2022-12-26 | ANGULAR-1
148 | Student | My cource material |  | Frontend | Pending | 2022-12-26 | 2022-12-26 | ANGULAR-2
149 | Student | Notifications |  | API | Pending | 2022-12-26 | 2022-12-26 | JAVA-1
151 | Student | Past Cources |  | API | Pending | 2022-12-26 | 2022-12-26 | JAVA-2
150 | Student | Notifications |  | Frontend | Pending | 2022-12-27 | 2022-12-27 | ANGULAR-1
152 | Student | Past Cources |  | Frontend | Pending | 2022-12-27 | 2022-12-27 | ANGULAR-2
153 | Student | Reply from Guruji |  | API | Pending | 2022-12-27 | 2022-12-27 | JAVA-1
155 | Student | Resources |  | API | Pending | 2022-12-27 | 2022-12-27 | JAVA-2
154 | Student | Resources |  | Frontend | Pending | 2022-12-28 | 2022-12-28 | ANGULAR-1
156 | Student | Resources - sorting |  | Frontend | Pending | 2022-12-28 | 2022-12-28 | ANGULAR-2
157 | Student | Resources - sorting |  | API | Pending | 2022-12-28 | 2022-12-28 | JAVA-1
158 | Student | Status of tasks & certifications |  | Frontend | Pending | 2022-12-29 | 2022-12-29 | ANGULAR-1
159 | Student | My task certificate view |  | API | Pending | 2023-01-02 | 2023-01-02 | JAVA-2
161 | Student | View Gratitude Msg |  | API | Pending | 2023-01-02 | 2023-01-02 | JAVA-1
160 | Student | View all Gratitude Msg |  | Frontend | Pending | 2023-01-03 | 2023-01-03 | ANGULAR-2
162 | Student | View tasks |  | Frontend | Pending | 2023-01-03 | 2023-01-03 | ANGULAR-1
163 | Student | World Wide Gratitude Msg |  | API | Pending | 2023-01-03 | 2023-01-03 | JAVA-2
165 | Student | Write Gratitude msg |  | API | Pending | 2023-01-03 | 2023-01-03 | JAVA-1
164 | Student | World Wide Gratitude Msg view |  | Frontend | Pending | 2023-01-04 | 2023-01-04 | ANGULAR-2
166 | Student | All my gratitude msg view |  | Frontend | Pending | 2023-01-04 | 2023-01-04 | ANGULAR-1
167 | Student | View tasks |  | API | Pending | 2023-01-04 | 2023-01-04 | JAVA-2
169 | Student | World wide gratitude msg view |  | API | Pending | 2023-01-04 | 2023-01-04 | JAVA-1
168 | Student | World wide gratitude msg |  | Frontend | Pending | 2023-01-05 | 2023-01-05 | ANGULAR-2
170 | Student | Write World wide gratitude msg view |  | Frontend | Pending | 2023-01-05 | 2023-01-05 | ANGULAR-1
171 | Mentor | Dashboard |  | API | Pending | 2023-01-05 | 2023-01-05 | JAVA-1
173 | Mentor | Dashboard count click |  | API | Pending | 2023-01-05 | 2023-01-05 | JAVA-2
172 | Mentor | Dashboard |  | Frontend | Pending | 2023-01-06 | 2023-01-06 | ANGULAR-1
174 | Mentor | Dashboard count click |  | Frontend | Pending | 2023-01-06 | 2023-01-06 | ANGULAR-2
175 | Mentor | Total applications assign to mentor |  | API | Pending | 2023-01-06 | 2023-01-06 | JAVA-1
177 | Mentor | Active students as on the day |  | API | Pending | 2023-01-06 | 2023-01-06 | JAVA-2
176 | Mentor | Total applications assign to mentor |  | Frontend | Pending | 2023-01-09 | 2023-01-09 | ANGULAR-1
178 | Mentor | Active students as on the day |  | Frontend | Pending | 2023-01-09 | 2023-01-09 | ANGULAR-2
179 | Mentor | View student - Profile |  | API | Pending | 2023-01-09 | 2023-01-09 | JAVA-1
181 | Mentor | View student - Cources Profile |  | API | Pending | 2023-01-09 | 2023-01-09 | JAVA-2
180 | Mentor | View student - Profile |  | Frontend | Pending | 2023-01-10 | 2023-01-10 | ANGULAR-1
182 | Mentor | View student - Cources Profile |  | Frontend | Pending | 2023-01-10 | 2023-01-10 | ANGULAR-2
183 | Mentor | View student - Donations |  | API | Pending | 2023-01-10 | 2023-01-10 | JAVA-1
185 | Mentor | View student - e Purcheses |  | API | Pending | 2023-01-10 | 2023-01-10 | JAVA-2
184 | Mentor | View student - Donations |  | Frontend | Pending | 2023-01-11 | 2023-01-11 | ANGULAR-1
186 | Mentor | View student - e Purcheses |  | Frontend | Pending | 2023-01-11 | 2023-01-11 | ANGULAR-2
187 | Mentor | View student - Volintering Details |  | API | Pending | 2023-01-11 | 2023-01-11 | JAVA-1
189 | Mentor | View student - Performance report |  | API | Pending | 2023-01-11 | 2023-01-11 | JAVA-2
188 | Mentor | View student - Volintering Details |  | Frontend | Pending | 2023-01-12 | 2023-01-12 | ANGULAR-1
190 | Mentor | View student - Performance report |  | Frontend | Pending | 2023-01-12 | 2023-01-12 | ANGULAR-2
191 | Mentor | Gradtitude msg forward |  | API | Pending | 2023-01-12 | 2023-01-12 | JAVA-1
193 | Mentor | Gradtitude msg chief menter |  | API | Pending | 2023-01-12 | 2023-01-12 | JAVA-2
192 | Mentor | Gradtitude msg unread |  | Frontend | Pending | 2023-01-13 | 2023-01-13 | ANGULAR-1
194 | Mentor | Gradtitude msg informed & denied |  | Frontend | Pending | 2023-01-13 | 2023-01-13 | ANGULAR-2
195 | Mentor | Gradtitude Msg editor |  | API | Pending | 2023-01-13 | 2023-01-13 | JAVA-1
196 | Mentor | Gradtitude msg summary |  | Frontend | Pending | 2023-01-16 | 2023-01-16 | ANGULAR-1
198 | Mentor | View certificate seeker |  | Frontend | Pending | 2023-01-16 | 2023-01-16 | ANGULAR-2
197 | Mentor | View certificate seeker |  | API | Pending | 2023-01-17 | 2023-01-17 | JAVA-2
199 | Mentor | Gurudakshana paid list |  | API | Pending | 2023-01-17 | 2023-01-17 | JAVA-1
200 | Mentor | Evaluation of task assignment list |  | Frontend | Pending | 2023-01-17 | 2023-01-17 | ANGULAR-1
202 | Mentor | Graditude Msg exclusive |  | Frontend | Pending | 2023-01-17 | 2023-01-17 | ANGULAR-2
201 | Mentor | Evaluation of task assignment |  | API | Pending | 2023-01-18 | 2023-01-18 | JAVA-2
203 | Mentor | list of voliters intrested |  | API | Pending | 2023-01-18 | 2023-01-18 | JAVA-1
204 | Mentor | list of voliters intrested |  | Frontend | Pending | 2023-01-18 | 2023-01-18 | ANGULAR-1
206 | Mentor | Guruji report |  | Frontend | Pending | 2023-01-18 | 2023-01-18 | ANGULAR-2
205 | Mentor | Messgae from Guruji |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-2
207 | Mentor | Response given to chief mentor and students |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-1
208 | Chief Mentor | Dashboard |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-1
210 | Chief Mentor | Dashboared count click |  | API | Pending | 2023-01-19 | 2023-01-19 | JAVA-2
209 | Chief Mentor | Dashboard |  | Frontend | Pending | 2023-01-20 | 2023-01-20 | ANGULAR-1
211 | Chief Mentor | Dashboared count click |  | Frontend | Pending | 2023-01-20 | 2023-01-20 | ANGULAR-2
212 | Chief Mentor | world wide app |  | API | Pending | 2023-01-20 | 2023-01-20 | JAVA-1
214 | Chief Mentor | My region application |  | API | Pending | 2023-01-20 | 2023-01-20 | JAVA-2
213 | Chief Mentor | world wide app |  | Frontend | Pending | 2023-01-23 | 2023-01-23 | ANGULAR-1
215 | Chief Mentor | My region application |  | Frontend | Pending | 2023-01-23 | 2023-01-23 | ANGULAR-2
216 | Chief Mentor | Manage exemptions |  | API | Pending | 2023-01-23 | 2023-01-23 | JAVA-1
218 | Chief Mentor | my mentors |  | API | Pending | 2023-01-23 | 2023-01-23 | JAVA-2
217 | Chief Mentor | Manage exemptions |  | Frontend | Pending | 2023-01-24 | 2023-01-24 | ANGULAR-1
219 | Chief Mentor | my mentors |  | Frontend | Pending | 2023-01-24 | 2023-01-24 | ANGULAR-2
220 | Chief Mentor | View student - Profile |  | API | Pending | 2023-01-24 | 2023-01-24 | JAVA-1
222 | Chief Mentor | View student - Performance details |  | API | Pending | 2023-01-24 | 2023-01-24 | JAVA-2
221 | Chief Mentor | View student - Profile |  | Frontend | Pending | 2023-01-25 | 2023-01-25 | ANGULAR-1
223 | Chief Mentor | View student - Performance details |  | Frontend | Pending | 2023-01-25 | 2023-01-25 | ANGULAR-2
224 | Chief Mentor | View student - Donations |  | API | Pending | 2023-01-25 | 2023-01-25 | JAVA-1
226 | Chief Mentor | View student - e Purcheses |  | API | Pending | 2023-01-25 | 2023-01-25 | JAVA-2
225 | Chief Mentor | View student - Donations |  | Frontend | Pending | 2023-01-27 | 2023-01-27 | ANGULAR-1
227 | Chief Mentor | View student - e Purcheses |  | Frontend | Pending | 2023-01-27 | 2023-01-27 | ANGULAR-2
228 | Chief Mentor | View student - Volintering Details |  | API | Pending | 2023-01-27 | 2023-01-27 | JAVA-1
230 | Chief Mentor | View student - Cources profile |  | API | Pending | 2023-01-27 | 2023-01-27 | JAVA-2
229 | Chief Mentor | View student - Volintering Details |  | Frontend | Pending | 2023-01-30 | 2023-01-30 | ANGULAR-1
231 | Chief Mentor | View student - Cources profile |  | Frontend | Pending | 2023-01-30 | 2023-01-30 | ANGULAR-2
232 | Chief Mentor | Gradtitude msg informed denied |  | API | Pending | 2023-01-30 | 2023-01-30 | JAVA-1
234 | Chief Mentor | Gradtitude msg - edit |  | API | Pending | 2023-01-30 | 2023-01-30 | JAVA-2
233 | Chief Mentor | Gradtitude msg - Unread |  | Frontend | Pending | 2023-01-31 | 2023-01-31 | ANGULAR-1
235 | Chief Mentor | Gradtitude msg circular msg |  | Frontend | Pending | 2023-01-31 | 2023-01-31 | ANGULAR-2
236 | Chief Mentor | Gradtitude msg -recomemded |  | API | Pending | 2023-01-31 | 2023-01-31 | JAVA-1
238 | Chief Mentor | View certificate seekar |  | API | Pending | 2023-01-31 | 2023-01-31 | JAVA-2
237 | Chief Mentor | Graditude summaryu |  | Frontend | Pending | 2023-02-01 | 2023-02-01 | ANGULAR-1
239 | Chief Mentor | View certificate seekar |  | Frontend | Pending | 2023-02-01 | 2023-02-01 | ANGULAR-2
240 | Chief Mentor | Gurudakshana seekar |  | API | Pending | 2023-02-01 | 2023-02-01 | JAVA-1
242 | Chief Mentor | Graditude msg - exclusive vn |  | API | Pending | 2023-02-01 | 2023-02-01 | JAVA-2
241 | Chief Mentor | Evalution task assignment |  | Frontend | Pending | 2023-02-02 | 2023-02-02 | ANGULAR-1
243 | Chief Mentor | list of volinters |  | Frontend | Pending | 2023-02-02 | 2023-02-02 | ANGULAR-2
244 | Chief Mentor | list of volinters |  | API | Pending | 2023-02-02 | 2023-02-02 | JAVA-1
246 | Chief Mentor | Manage exemptions |  | API | Pending | 2023-02-02 | 2023-02-02 | JAVA-2
245 | Chief Mentor | Manage exemptions |  | Frontend | Pending | 2023-02-03 | 2023-02-03 | ANGULAR-1
248 | Chief Mentor | read graditude msg with names - region |  | API | Pending | 2023-02-03 | 2023-02-03 | JAVA-1
250 | Chief Mentor | Report of automatic remove |  | API | Pending | 2023-02-03 | 2023-02-03 | JAVA-2
247 | Chief Mentor | message from guruji |  | Frontend | Pending | 2023-02-06 | 2023-02-06 | ANGULAR-2
249 | Chief Mentor | read graditude msg with names - all |  | Frontend | Pending | 2023-02-06 | 2023-02-06 | ANGULAR-1
252 | Chief Mentor | report of graditude reading |  | API | Pending | 2023-02-06 | 2023-02-06 | JAVA-1
254 | Guruji | Dashboard |  | API | Pending | 2023-02-06 | 2023-02-06 | JAVA-2
251 | Chief Mentor | Report of automatic remove |  | Frontend | Pending | 2023-02-07 | 2023-02-07 | ANGULAR-2
253 | Chief Mentor | message given to studen and mentor |  | Frontend | Pending | 2023-02-07 | 2023-02-07 | ANGULAR-1
255 | Guruji | Dashboard |  | Frontend | Pending | 2023-02-07 | 2023-02-07 | ANGULAR-2
256 | Guruji | Dashboared Cources report |  | API | Pending | 2023-02-07 | 2023-02-07 | JAVA-1
258 | Guruji | Guruji msg - exclusive vn |  | API | Pending | 2023-02-07 | 2023-02-07 | JAVA-2
257 | Guruji | Dashboared Cources report |  | Frontend | Pending | 2023-02-08 | 2023-02-08 | ANGULAR-1
259 | Guruji | Guruji msg - all students |  | Frontend | Pending | 2023-02-08 | 2023-02-08 | ANGULAR-2
260 | Guruji | Message to chief mentor |  | API | Pending | 2023-02-08 | 2023-02-08 | JAVA-1
262 | Guruji | Recommended msg |  | API | Pending | 2023-02-08 | 2023-02-08 | JAVA-2
261 | Guruji | Recommended msg list |  | Frontend | Pending | 2023-02-09 | 2023-02-09 | ANGULAR-1
263 | Guruji | Report of graditude reading of students |  | Frontend | Pending | 2023-02-09 | 2023-02-09 | ANGULAR-2
264 | Guruji | Report of graditude reading of schief mentors |  | API | Pending | 2023-02-09 | 2023-02-09 | JAVA-1
266 | Guruji | View student - Profile |  | API | Pending | 2023-02-09 | 2023-02-09 | JAVA-2
265 | Guruji | View student - Profile |  | Frontend | Pending | 2023-02-10 | 2023-02-10 | ANGULAR-1
267 | Guruji | View student - Performance details |  | Frontend | Pending | 2023-02-10 | 2023-02-10 | ANGULAR-2
268 | Guruji | View student - Performance details |  | API | Pending | 2023-02-10 | 2023-02-10 | JAVA-1
270 | Guruji | View student - Donations |  | API | Pending | 2023-02-10 | 2023-02-10 | JAVA-2
269 | Guruji | View student - Donations |  | Frontend | Pending | 2023-02-13 | 2023-02-13 | ANGULAR-1
271 | Guruji | View student - e Purcheses |  | Frontend | Pending | 2023-02-13 | 2023-02-13 | ANGULAR-2
272 | Guruji | View student - e Purcheses |  | API | Pending | 2023-02-14 | 2023-02-14 | JAVA-1
274 | Guruji | View student - Volintering Details |  | API | Pending | 2023-02-14 | 2023-02-14 | JAVA-2
273 | Guruji | View student - Volintering Details |  | Frontend | Pending | 2023-02-15 | 2023-02-15 | ANGULAR-1
275 | Guruji | View student - Cources profile |  | Frontend | Pending | 2023-02-15 | 2023-02-15 | ANGULAR-2
276 | Guruji | View student - Cources profile |  | API | Pending | 2023-02-15 | 2023-02-15 | JAVA-1
278 | Guruji | Region summary |  | API | Pending | 2023-02-15 | 2023-02-15 | JAVA-2
277 | Guruji | Region summary |  | Frontend | Pending | 2023-02-16 | 2023-02-16 | ANGULAR-1
279 | Guruji | Users |  | Frontend | Pending | 2023-02-16 | 2023-02-16 | ANGULAR-2
280 | Guruji | Users |  | API | Pending | 2023-02-16 | 2023-02-16 | JAVA-1
281 | Guruji | world wide application |  | API | Pending | 2023-02-16 | 2023-02-16 | JAVA-2
281 | Guruji | replies given to graditity admin |  | Frontend | Pending | 2023-02-17 | 2023-02-17 | ANGULAR-1
282 | Guruji | world wide application |  | Frontend | Pending | 2023-02-17 | 2023-02-17 | ANGULAR-2
283 | Gratitude-admin | Dashboard |  | API | Pending | 2023-02-20 | 2023-02-20 | JAVA-1
285 | Gratitude-admin | world wide Application |  | API | Pending | 2023-02-20 | 2023-02-20 | JAVA-2
284 | Gratitude-admin | Dashboard |  | Frontend | Pending | 2023-02-21 | 2023-02-21 | ANGULAR-1
286 | Gratitude-admin | World Wide Application |  | Frontend | Pending | 2023-02-21 | 2023-02-21 | ANGULAR-2
287 | Gratitude-admin | Number of Mentor |  | API | Pending | 2023-02-21 | 2023-02-21 | JAVA-1
289 | Gratitude-admin | World wide Application |  | API | Pending | 2023-02-21 | 2023-02-21 | JAVA-2
288 | Gratitude-admin | Number of Mentor |  | Frontend | Pending | 2023-02-22 | 2023-02-22 | ANGULAR-1
290 | Gratitude-admin | world Wide Application |  | Frontend | Pending | 2023-02-22 | 2023-02-22 | ANGULAR-2
291 | Gratitude-admin | Manage exemptions |  | API | Pending | 2023-02-22 | 2023-02-22 | JAVA-1
293 | Gratitude-admin | View-Student |  | API | Pending | 2023-02-22 | 2023-02-22 | JAVA-2
292 | Gratitude-admin | Manage exemptions |  | Frontend | Pending | 2023-02-24 | 2023-02-24 | ANGULAR-1
294 | Gratitude-admin | View-Student |  | Frontend | Pending | 2023-02-24 | 2023-02-24 | ANGULAR-2
295 | Gratitude-admin | Course-profile |  | API | Pending | 2023-02-24 | 2023-02-24 | JAVA-1
297 | Gratitude-admin | Donations management |  | API | Pending | 2023-02-24 | 2023-02-24 | JAVA-2
296 | Gratitude-admin | Course-profile |  | Frontend | Pending | 2023-02-27 | 2023-02-27 | ANGULAR-1
298 | Gratitude-admin | Donations management |  | Frontend | Pending | 2023-02-27 | 2023-02-27 | ANGULAR-2
299 | Gratitude-admin | e-purchase information |  | API | Pending | 2023-02-27 | 2023-02-27 | JAVA-1
301 | Gratitude-admin | Voulterring Details |  | API | Pending | 2023-02-27 | 2023-02-27 | JAVA-2
300 | Gratitude-admin | e-purchase information |  | Frontend | Pending | 2023-02-28 | 2023-02-28 | ANGULAR-1
302 | Gratitude-admin | Voulterring Details |  | Frontend | Pending | 2023-02-28 | 2023-02-28 | ANGULAR-2
303 | Gratitude-admin | performance-report |  | API | Pending | 2023-02-28 | 2023-02-28 | JAVA-1
305 | Gratitude-admin | Alerts-View |  | API | Pending | 2023-02-28 | 2023-02-28 | JAVA-2
304 | Gratitude-admin | performance-report |  | Frontend | Pending | 2023-03-01 | 2023-03-01 | ANGULAR-1
306 | Gratitude-admin | Alerts-View |  | Frontend | Pending | 2023-03-01 | 2023-03-01 | ANGULAR-2
307 | Gratitude-admin | Alerts |  | API | Pending | 2023-03-01 | 2023-03-01 | JAVA-1
309 | Gratitude-admin | Black List users |  | API | Pending | 2023-03-01 | 2023-03-01 | JAVA-2
308 | Gratitude-admin | Alerts |  | Frontend | Pending | 2023-03-02 | 2023-03-02 | ANGULAR-1
310 | Gratitude-admin | Black List users |  | Frontend | Pending | 2023-03-02 | 2023-03-02 | ANGULAR-2
311 | Gratitude-admin | circulation-messages |  | API | Pending | 2023-03-02 | 2023-03-02 | JAVA-1
313 | Gratitude-admin | circulation-messages -All messages |  | API | Pending | 2023-03-02 | 2023-03-02 | JAVA-2
312 | Gratitude-admin | circulation-messages |  | Frontend | Pending | 2023-03-03 | 2023-03-03 | ANGULAR-1
314 | Gratitude-admin | circulation-messages -All messages |  | Frontend | Pending | 2023-03-03 | 2023-03-03 | ANGULAR-2
315 | Gratitude-admin | Guruji-reply |  | API | Pending | 2023-03-03 | 2023-03-03 | JAVA-1
317 | Gratitude-admin | My-course-material |  | API | Pending | 2023-03-03 | 2023-03-03 | JAVA-2
316 | Gratitude-admin | Guruji-reply |  | Frontend | Pending | 2023-03-06 | 2023-03-06 | ANGULAR-1
318 | Gratitude-admin | My-course-material |  | Frontend | Pending | 2023-03-06 | 2023-03-06 | ANGULAR-2
319 | Gratitude-admin | Gratitudemessage-VN Experience |  | API | Pending | 2023-03-06 | 2023-03-06 | JAVA-1
321 | Gratitude-admin | Gratitudemessage-VN Experience -view |  | API | Pending | 2023-03-06 | 2023-03-06 | JAVA-2
320 | Gratitude-admin | Gratitudemessage-VN Experience |  | Frontend | Pending | 2023-03-07 | 2023-03-07 | ANGULAR-1
322 | Gratitude-admin | Gratitudemessage-VN Experience -view |  | Frontend | Pending | 2023-03-07 | 2023-03-07 | ANGULAR-2
323 | Gratitude-admin | Glimpes |  | API | Pending | 2023-03-07 | 2023-03-07 | JAVA-1
325 | Gratitude-admin | message from Guruji |  | API | Pending | 2023-03-07 | 2023-03-07 | JAVA-2
324 | Gratitude-admin | Glimpes |  | Frontend | Pending | 2023-03-08 | 2023-03-08 | ANGULAR-1
326 | Gratitude-admin | message from Guruji |  | Frontend | Pending | 2023-03-08 | 2023-03-08 | ANGULAR-2
327 | Gratitude-admin | Notifications |  | API | Pending | 2023-03-08 | 2023-03-08 | JAVA-1
329 | Gratitude-admin | Parameters |  | API | Pending | 2023-03-08 | 2023-03-08 | JAVA-2
328 | Gratitude-admin | Notifications |  | Frontend | Pending | 2023-03-09 | 2023-03-09 | ANGULAR-1
330 | Gratitude-admin | Parameters |  | Frontend | Pending | 2023-03-09 | 2023-03-09 | ANGULAR-2
331 | Gratitude-admin | Recommended-messages |  | API | Pending | 2023-03-09 | 2023-03-09 | JAVA-1
333 | Gratitude-admin | Recommended-messages All-messages |  | API | Pending | 2023-03-09 | 2023-03-09 | JAVA-2
332 | Gratitude-admin | Recommended-messages |  | Frontend | Pending | 2023-03-10 | 2023-03-10 | ANGULAR-1
334 | Gratitude-admin | Recommended-messages All-messages |  | Frontend | Pending | 2023-03-10 | 2023-03-10 | ANGULAR-2
335 | Gratitude-admin | report of replies of guruji |  | API | Pending | 2023-03-10 | 2023-03-10 | JAVA-1
337 | Gratitude-admin | summary |  | API | Pending | 2023-03-10 | 2023-03-10 | JAVA-2
336 | Gratitude-admin | report of replies of guruji |  | Frontend | Pending | 2023-03-13 | 2023-03-13 | ANGULAR-1
338 | Gratitude-admin | summary |  | Frontend | Pending | 2023-03-13 | 2023-03-13 | ANGULAR-2
339 | Gratitude-admin | Task Assignment |  | API | Pending | 2023-03-13 | 2023-03-13 | JAVA-1
341 | Gratitude-admin | Create Task |  | API | Pending | 2023-03-13 | 2023-03-13 | JAVA-2
340 | Gratitude-admin | Task Assignment |  | Frontend | Pending | 2023-03-14 | 2023-03-14 | ANGULAR-1
342 | Gratitude-admin | Create Task |  | Frontend | Pending | 2023-03-14 | 2023-03-14 | ANGULAR-2
18 | Admin | World wide applications | Sumukesh | API | Open |  |  | JAVA-1
19 | Admin | World wide applications | Ajith R | Frontend | Open |  |  | ANGULAR-1
343 | QA | SIT |  |  | Pending
344 | QA | UAT1 |  |  | Pending
345 | QA | UAT2 |  |  | Pending
346 | QA | Go Live |  |  | Pending

## admin all tables
m_course_category
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_course_category | catergory_id | primary-key | INT | 10
2 | ADMIN | m_course_category | catergory_name |  | Varchar | 55 | (Student,Admin,Mentor,chief-mentor,mentor,guruji)
3 | ADMIN | m_course_category | created-date |  | Date
4 | ADMIN | m_course_category | created_by |  | Varchar | 55
5 | ADMIN | m_course_category | updated_date |  | date
6 | ADMIN | m_course_category | updated_by |  | Varchar | 55
7 | ADMIN | m_course_category | is_active |  | Varchar | 10
m_course
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_courses | course_id | primary-key | INT | 10
2 | ADMIN | m_courses | course_name |  | Varchar | 55
3 | ADMIN | m_courses | course_type |  | Varchar | 55
4 | ADMIN | m_courses | section |  | section | 55
5 | ADMIN | m_courses | course_duration |  | int | 55
6 | ADMIN | m_courses | Verficication_required |  | Varchar | 10 | Verfication(yes or No)
7 | ADMIN | m_courses | created-date |  | Date
8 | ADMIN | m_courses | created_by |  | Varchar | 55
9 | ADMIN | m_courses | updated_date |  | date
10 | ADMIN | m_courses | updated_by |  | Varchar | 55
11 | ADMIN | m_courses | is_active |  | Varchar | 10
Table_name: course_media_files
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | course_media_files | Id | primary-key | int | 55
2 | ADMIN | course_media_files | courses_Id |  | int | 55
3 | ADMIN | course_media_files | courses_type |  | varchar | 255 | VideoType(short,liveclasses,pratice)
4 | ADMIN | course_media_files | section |  | varchar | 255
5 | ADMIN | course_media_files | course_duration |  | int | 55
6 | ADMIN | course_media_files | verfication |  | varchar | 10 | Verfication(yes or No)
7 | ADMIN | course_media_files | created-date |  | Date
8 | ADMIN | course_media_files | created_by |  | Varchar | 55
9 | ADMIN | course_media_files | updated_date |  | date
10 | ADMIN | course_media_files | updated_by |  | Varchar | 55
11 | ADMIN | course_media_files | is_active |  | Varchar | 10
m_exceptions
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_exceptions | exception_id | primary-key | int | 10
2 | ADMIN | m_exceptions | exception_Desc |  |  | 255
3 | ADMIN | m_exceptions | created-date |  | Date
4 | ADMIN | m_exceptions | created_by |  | Varchar | 55
5 | ADMIN | m_exceptions | updated_date |  | date
6 | ADMIN | m_exceptions | updated_by |  | Varchar | 55
7 | ADMIN | m_exceptions | is_active |  | Varchar | 10
course_exceptions
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | course_exceptions | course_id | primary-key | int | 10
2 | ADMIN | course_exceptions | exceptions_id | ForigenKey(m_exception) | int | 10
3 | ADMIN | course_exceptions | status |  | varchar | 255
|  |  | created-date |  | Date
|  |  | created_by |  | Varchar | 55
|  |  | updated_date |  | date
|  |  | updated_by |  | Varchar | 55
|  |  | is_active |  | Varchar | 10
table_name: m_student_status
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_student_status | student_status_Id | primary-key | int | 10
2 | ADMIN | m_student_status | student_status |  | varchar
| ADMIN | m_student_status | created-date |  | Date |  | active ,inactive,block,
| ADMIN | m_student_status | created_by |  | Varchar | 55
| ADMIN | m_student_status | updated_date |  | date
| ADMIN | m_student_status | updated_by |  | Varchar | 55
| ADMIN | m_student_status | is_active |  | Varchar | 10
student_course_assignement
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | student_course_assignement | id | primary-key | int | 55
2 | ADMIN | student_course_assignement | student_id |  | int | 55
3 | ADMIN | student_course_assignement | course_Id | ForigenKey(m_exception) | int | 55
4 | ADMIN | student_course_assignement | batch_Id |  | int | 55
5 | ADMIN | student_course_assignement | created-date |  | Date
6 | ADMIN | student_course_assignement | created_by |  | Varchar | 55
7 | ADMIN | student_course_assignement | updated_date |  | date
8 | ADMIN | student_course_assignement | updated_by |  | Varchar | 55
9 | ADMIN | student_course_assignement | is_active |  | Varchar | 10
table_name : student_reporting_mapping
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | student_reporting_mapping | id | primary-key | int | 55
2 | ADMIN | student_reporting_mapping | Admin_id |  | int | 55
3 | ADMIN | student_reporting_mapping | student_id |  | int | 55
4 | ADMIN | student_reporting_mapping | cheif_mentorId |  | int | 55
5 | ADMIN | student_reporting_mapping | mentor_id |  | int | 55
6 | ADMIN | student_reporting_mapping | guruji_id |  | int | 55
7 | ADMIN | student_reporting_mapping | created-date |  | Date
8 | ADMIN | student_reporting_mapping | created_by |  | Varchar | 55
9 | ADMIN | student_reporting_mapping | updated_date |  | date
10 | ADMIN | student_reporting_mapping | updated_by |  | Varchar | 55
11 | ADMIN | student_reporting_mapping | is_active |  | Varchar | 10
table: registration
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | registration | registration_id | primary-key | int | 10
2 | ADMIN | registration | registration_email |  | varchar | 255
3 | ADMIN | registration | registration_name |  | varchar | 55
4 | ADMIN | registration | registration_profession | ForigenKey(profession) | varchar | 10
5 | ADMIN | registration | registration_gender_id | ForigenKey(gender) | int | 10
6 | ADMIN | registration | registration_qualification_id | ForigenKey(qualification) | int | 10
7 | ADMIN | registration | created-date |  | Date
8 | ADMIN | registration | created_by |  | Varchar | 55
9 | ADMIN | registration | updated_date |  | date
10 | ADMIN | registration | updated_by |  | Varchar | 55
11 | ADMIN | registration | is_active |  | Varchar | 10
tablename :profession
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | profession | profession_id |  | int | 10
2 | ADMIN | profession | profession_name | primary-key | varchar | 155
3 | ADMIN | profession | created-date |  | Date
4 | ADMIN | profession | created_by |  | Varchar | 55
5 | ADMIN | profession | updated_date |  | date
6 | ADMIN | profession | updated_by |  | Varchar | 55
7 | ADMIN | profession | is_active |  | Varchar | 10
Gender
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | Gender | gender_id |  | int | 10
2 | ADMIN | Gender | gender_type | primary-key | varchar | 155
3 | ADMIN | Gender | created-date |  | Date
4 | ADMIN | Gender | created_by |  | Varchar | 55
5 | ADMIN | Gender | updated_date |  | date
6 | ADMIN | Gender | updated_by |  | Varchar | 55
7 | ADMIN | Gender | is_active |  | Varchar | 10
table_name:qulification
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | qualification | qualificaation_id |  | int | 10
2 | ADMIN | qualification | qualificaation_name | primary-key | varchar | 155
3 | ADMIN | qualification | created-date |  | Date
4 | ADMIN | qualification | created_by |  | Varchar | 55
5 | ADMIN | qualification | updated_date |  | date
6 | ADMIN | qualification | updated_by |  | Varchar | 55
7 | ADMIN | qualification | is_active |  | Varchar | 10
table_name:Admission_status
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | Admission_status | Admission_id | primary-key | int | 10
2 | ADMIN | Admission_status | Admission_status |  | varchar | 155
3 | ADMIN | Admission_status | created-date |  | Date
4 | ADMIN | Admission_status | created_by |  | Varchar | 55
5 | ADMIN | Admission_status | updated_date |  | date
6 | ADMIN | Admission_status | updated_by |  | Varchar | 55
7 | ADMIN | Admission_status | is_active |  | Varchar | 10
completion_status
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | completion_status | completion_id | primary-key | int | 10
2 | ADMIN | completion_status | completion_name |  | varchar | 155 | completed,certfied,removed
3 | ADMIN | completion_status | created-date |  | Date
4 | ADMIN | completion_status | created_by |  | Varchar | 55
5 | ADMIN | completion_status | updated_date |  | date
6 | ADMIN | completion_status | updated_by |  | Varchar | 55
7 | ADMIN | completion_status | is_active |  | Varchar | 10
tablename:perfromace_grading
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | perfromace_grading | grading_Id | primary-key
2 | ADMIN | perfromace_grading | performance_name |  |  |  | good,poor,average
3 | ADMIN | perfromace_grading | created-date |  | Date
4 | ADMIN | perfromace_grading | created_by |  | Varchar | 55
5 | ADMIN | perfromace_grading | updated_date |  | date
6 | ADMIN | perfromace_grading | updated_by |  | Varchar | 55
7 | ADMIN | perfromace_grading | is_active |  | Varchar | 10
table_name:m_course_perfromance_rating
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | m_course_perfromance_rating | rating_id | primary-key
2 | ADMIN | m_course_perfromance_rating | course_Id | forgien-Key(m_courses)
3 | ADMIN | m_course_perfromance_rating | perfromance_Id | forgien-Key(performance_mointering)
4 | ADMIN | m_course_perfromance_rating | grading_Id | grading_Id(perfromace_grading)
3 | ADMIN | m_course_perfromance_rating | created-date |  | Date
4 | ADMIN | m_course_perfromance_rating | created_by |  | Varchar | 55
5 | ADMIN | m_course_perfromance_rating | updated_date |  | date
6 | ADMIN | m_course_perfromance_rating | updated_by |  | Varchar | 55
7 | ADMIN | m_course_perfromance_rating | is_active |  | Varchar | 10
table_name:student_pratice_session
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | student_pratice_session | Id | primary-key | int | 10
2 | ADMIN | student_pratice_session | student_id | forgien_key(student_course_assignement) | int | 10
3 | ADMIN | student_pratice_session | course_id | forgien-Key(m_courses) | int | 10
4 | ADMIN | student_pratice_session | date |  | Date
3 | ADMIN | student_pratice_session | Attended_duration |  | Date
4 | ADMIN | student_pratice_session | percentage_completion |  | int | 10
5 | ADMIN | student_pratice_session | created-date |  | Date
6 | ADMIN | student_pratice_session | created_by |  | Varchar | 55
7 | ADMIN | student_pratice_session | updated_date |  | date
8 | ADMIN | student_pratice_session | updated_by |  | Varchar | 55
9 | ADMIN | student_pratice_session | is_active |  | Varchar | 10
table_name:alert
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | alert | id | primary-key | int | 10
2 | ADMIN | alert | category_id | forigenkey(M_course_category)
3 | ADMIN | alert | alert_desc
4 | ADMIN | alert | startdate
5 | ADMIN | alert | enddate
6 | ADMIN | alert | file_name
7 | ADMIN | alert | created-date |  | Date
8 | ADMIN | alert | created_by |  | Varchar | 55
9 | ADMIN | alert | updated_date |  | date
10 | ADMIN | alert | updated_by |  | Varchar | 55
11 | ADMIN | alert | is_active |  | Varchar | 10
table_name:audio_category
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | audio_category | id | primary-key | int | 10
2 | ADMIN | audio_category | aduio_name |  | Varchar
3 | ADMIN | audio_category | audio_category |  | Varchar
4 | ADMIN | audio_category | created-date |  | Date
5 | ADMIN | audio_category | created_by |  | Varchar | 55
6 | ADMIN | audio_category | updated_date |  | date
7 | ADMIN | audio_category | updated_by |  | Varchar | 55
8 | ADMIN | audio_category | is_active |  | Varchar | 10
tablename:audio_management
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | audio_management | id | primary-key | int | 10
2 | ADMIN | audio_management | course_id | forigen_key | int | 10
3 | ADMIN | audio_management | audio_category_id |  | int | 10
4 | ADMIN | audio_management | upload_category |  | Varchar | 55
5 | ADMIN | audio_management | audio_type |  | Varchar | 55
6 | ADMIN | audio_management | audio_title |  | Varchar | 55
7 | ADMIN | audio_management | audio_desc |  | Varchar | 55
8 | ADMIN | audio_management | audio_duration |  | int | 10
9 | ADMIN | audio_management | metakey |  | Varchar | 55
10 | ADMIN | audio_management | created-date |  | Date
11 | ADMIN | audio_management | created_by |  | Varchar | 55
12 | ADMIN | audio_management | updated_date |  | date
13 | ADMIN | audio_management | updated_by |  | Varchar | 55
14 | ADMIN | audio_management | is_active |  | Varchar | 10
tablename:banner
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | banner | id | primary-key | int
2 | ADMIN | banner | banner_type |  | Varchar
3 | ADMIN | banner | title |  | Varchar
4 | ADMIN | banner | desc |  | Varchar
5 | ADMIN | banner | date |  | date
6 | ADMIN | banner | created-date |  | Date
7 | ADMIN | banner | created_by |  | Varchar | 55
8 | ADMIN | banner | updated_date |  | date
9 | ADMIN | banner | updated_by |  | Varchar | 55
10 | ADMIN | banner | is_active |  | Varchar | 10
tablename:course_material_category
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | course_material_category | id | primary-key | id
2 | ADMIN | course_material_category | category_name | forigen_key | Varchar |  | (techinical,scentific,special/day)
3 | ADMIN | course_material_category | created-date |  | Date
4 | ADMIN | course_material_category | created_by |  | Varchar | 55
5 | ADMIN | course_material_category | updated_date |  | date
6 | ADMIN | course_material_category | updated_by |  | Varchar | 55
7 | ADMIN | course_material_category | is_active |  | Varchar | 10
tablename:notification
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | notification | id | primary-key | int
2 | ADMIN | notification | category_id | forigen_key | int
3 | ADMIN | notification | noticfication_title |  | Varchar
4 | ADMIN | notification | file_name |  | Varchar
5 | ADMIN | notification | noticfication_desc |  | Varchar
6 | ADMIN | notification | created-date |  | Date
7 | ADMIN | notification | created_by |  | Varchar | 55
8 | ADMIN | notification | updated_date |  | date
9 | ADMIN | notification | updated_by |  | Varchar | 55
10 | ADMIN | notification | is_active |  | Varchar | 10
Roles
S.No | Module | sub-Module | parameter | parameterDetails | length
1 | Admin | Roles | role_id | id | 55
2 | Admin | Roles | role_name | varchar | 55
6 | ADMIN | notification | created-date |  | Date
7 | ADMIN | notification | created_by |  | Varchar | 55
8 | ADMIN | notification | updated_date |  | date
9 | ADMIN | notification | updated_by |  | Varchar | 55
10 | ADMIN | notification | is_active |  | Varchar | 10
tablename:users
S.No | Module | Table-Name | value | Key | Attributes | length
1 | ADMIN | users | user_id
2 | ADMIN | users | user_name | primary_key
3 | ADMIN | users | role_id
4 | ADMIN | users | password
5 | ADMIN | users | created-date |  | Date
6 | ADMIN | users | created_by |  | Varchar | 55
7 | ADMIN | users | updated_date |  | date
8 | ADMIN | users | updated_by |  | Varchar | 55
9 | ADMIN | users | is_active |  | Varchar | 10